## DLR-1 (hidden)
DLR& DPR Details
Contractor : Dayakar Electricals
Date | Tower -B |  |  |  |  | Tower -E
| Planned Works |  | Manpower (No's) | Work Status By EOD/ DPR | Remarks | PLANNED | Manpower (No's) | Status | Remarks
20-11-2025 | 1 | 2203 checking | 2
| 2 | 2nd floor mockup | 2
| 3 | 12&13 floor DB | 2
| 4 | staircase | 2
Total
| 1 | 29 floor communication | 2
| 2 | 21th floor toilet | 2
| 3 | staire case wiring | 1
| 4 | 12th floor toilet wiring | 2
Total
| 1 | 23 floor toilet wiring | 2
| 2 | 30th floor communication | 2
| 3 | 202 Switch board fixing | 3
| 4 | 1st floor foot lamp work | 2
Man power
| 1 | 30th floor communication | 2
| 2 | 202 Switch board fixing | 3
| 3 | 1st floor foot lamp work | 2
Man power
| 1 | 2203 Checking | 2
| 2 | 13th floor flat | 4
| 3 | 2nd floor foot lamp work | 2
Man power
| 1 | 16th floor toilet | 2
| 2 | 2nd floor foot lamp work | 2
Man power
| 1 | 12th & 13th floor DB | 1
| 2 | 2nd floor | 1
Man power
| 1 | 22 floor communication | 1
| 2 | 14th floor DB | 1
| 3 | lift shaft work | 3
| 4 | 19th floor foot lamp | 2
Man power
| 1 | 2203 Continuity Checking | 2
| 2 | lift shaft work | 4
| 3 | 19th floor foot lamp | 2
Man power
| 1 | 3002 flexible fixing | 1
| 2 | lift shaft work | 2
| 3 | 20th floor foot lamp | 2
Man power
| 1 | 3002 flexible fixing | 1
| 2 | lift shaft work | 3
Man power
| 1 | lift shaft work | 3
| 2 | 17th floor toilet | 2
| 3 | 3001 Ac Box fixing | 2
| 4 | 17th Fa Points | 2
|  | Man power | 9
| 1 | lift shaft work | 3
| 2 | B1 Slab Conduiting | 2
| 3 | 12th&13th Floor DB | 1
|  | Man power | 6
| 1 | lift shaft work | 3
| 2 | Club House | 2
|  | Man power | 5
| 1 | lift shaft work | 3
| 2 | B1 Slab Conduiting | 2
| 3 | 3rd Floor Corridor | 2
|  | Man power | 7
| 1 | 12th floor DB packing | 2
| 2 | B1 Slab Conduiting | 2
| 3 | 3rd Floor Corridor | 2
|  | Man power | 6
| 1 | 13 Floor DB packing | 2
|  | Man power | 2
| 1 | 11 th floor toilet | 2
| 2 | 16th floor toilet | 2
| 3 | 31st floor DB Fixing | 2
| 4 | 3rd floor celling lp marking | 2
|  | Man power | 8
| 1 | 3rd floor corridor | 2
| 2 | B1 Slab Conduiting | 2
| 3 | 31st floor DB Fixing | 2
| 4 | 2303 checking | 2
|  | Man power | 8
| 1 | 3rd floor corridor | 2
| 2 | 3rd floor Board cleaning | 2
| 3 | 2nd floor QC points | 2
| 4 | 16th DB packing | 2
|  | Man power | 8
| 1 | 3rd floor corridor | 2
| 2 | 3rd floor Board cleaning | 2
| 3 | 31st floor Knx Wiring | 2
| 4 | 16th and 15th toilet Work | 2
|  | Man power | 8
| 1 | 3rd floor corridor | 3
| 2 | 5th floor corridor wiring | 3
| 3 | 31st floor communication | 2
| 4 | 15th toilet Work | 1
|  | Man power | 9
| 1 | 3rd floor corridor | 4
| 2 | 5th floor corridor wiring | 3
| 3 | 17th18 toilet Work | 2
|  | Man power | 9
| 1 | 17thtoilet Work | 2
|  | Man power | 2
| 1 | 4rd floor corridor | 2
| 2 | 6th floor corridor wiring | 2
|  | Man power | 4
| 1 | 4rd floor corridor | 2
| 2 | 7th floor corridor wiring | 2
| 3 | 2303 Checking | 2
|  | Man power | 6
| 1 | 6rd floor corridor | 2
| 2 | 7th floor corridor wiring | 2
| 3 | 2302 Checking | 2
|  | Man power | 6
| 1 | 8rd floor corridor | 2
| 2 | 7th floor corridor wiring | 2
| 3 | 2302 Checking | 2
|  | Man power | 6
| 1 | 3102 wiring | 2
|  | Man power | 2
| 1 | 3201 wiring | 2
|  | Man power | 2
| 1 | 18th floor DB Packing | 1
| 2 | 22nd floor DB | 1
| 3 | 4th floor LP marking | 2
| 4 | 18th toilet Work | 2
|  | Man power | 6
| 1 | 22nd floor snag | 2
| 2 | 4th floor LP marking | 2
| 3 | 24th floor toilte work | 2
| 4 | 201 QC snag points | 1
| 5 | 22nd floor cutting chepping | 2
|  | Man power | 9
| 1 | 26th Floor toilte work | 2
| 2 | 2nd floor corridor conduting | 2
| 3 | passanger lift2 open conduting | 2
| 4 | 22nd floor cutting chepping | 2
|  | Man power | 8
| 1 | 18th Floor toilte work | 2
| 2 | 2nd floor corridor conduting | 2
| 3 | passanger lift2 open conduting | 2
| 4 | 2302&201 checking | 2
|  | Man power | 8
| 1 | 2nd floor corridor conduting | 2
| 2 | 3103 wiring | 2
| 3 | 401 LP marking | 2
| 4 | 27th toilet Work | 2
|  | Man power | 8
| 1 | 2nd floor corridor conduting | 2
| 2 | 23,24,25 Floor DB packing | 1
|  | Man power | 3
| 1 | 2nd floor corridor conduting | 4
| 2 | 3103 wiring | 2
| 3 | 27th toilet Work | 2
|  | Man power | 8
| 1 | 2nd &4th floor corridor conduting | 4
| 2 | 31st wiring | 4
|  | Man power | 8
| 1 | 5th 6th floor corridor conduting | 4
| 2 | 3203 wiring | 2
| 3 | 30 ledgewall | 2
| 4 | 27th toilet Work | 2
|  | Man power | 10
| 1 | 7th floor corridor wiring | 2
| 2 | 31&31 flat wiring | 2
| 3 | 28th floor toilte work | 2
| 4 | 31 floor ledge wall | 1
| 5 | 8th floor foot lamp fixing | 1
|  | Man power | 8
| 1 | 7th floor corridor wiring | 2
| 2 | 2301 checking | 2
| 3 | 14th floor toilte work | 2
| 4 | lmr room and earth strip | 4
| 5 | 4th floor lp marking | 2
|  | Man power | 12
| 1 | 7th floor corridor wiring | 2
| 2 | 2301 wiring checking | 2
| 3 | earth strip work | 2
| 4 | 31 st toilet Work | 2
|  | Man power | 8
| 1 | 24th floor checking | 2
| 2 | 24 th flooe foot lamp cutting | 2
| 3 | earth strip work | 1
|  | Man power | 5
| 1 | 24Th floor checking | 2
| 2 | 24th floor foootlamp cutting chepping | 2
| 3 | Lmr room | 2
|  | Man power | 6
| 1 | 24th floor foootlamp cutting chepping | 2
| 2 | 2nd floor c | 2
| 3 | Toilte work | 1
| 4 | Phase 2 basment temporary lighting | 2
|  | Man power | 7
| 1 | corridor work | 2
| 2 | 2nd floor actuators fixing | 2
| 3 | phase 2 basment temporary lighting | 2
|  | Man power | 6
| 1 | lift rectification | 2
| 2 | 2nd floor actuators fixing | 1
| 3 | FAPA Counduting | 1
|  | Man power | 4
| 1 | Club house slab conduiting | 4
| 2 | 2nd floor actuators fixing | 2
| 3 | 17th floor FAPA Counduting | 2
|  | Man power | 8
| 1 | 5th floor LP marking | 2
| 2 | 17th floor FAPA Counduting | 1
|  | Man power | 3
| 1 | 27th floor tagging | 2
| 2 | 3rd floor Ac socket fixing | 3
| 3 | 25th floor FAPA Counduting | 2
|  | Man power | 7
| 1 | 29th floor tagging | 2
| 2 | 4th floor GLD wiring | 2
| 3 | 28th floor FAPA Counduting | 2
|  | Man power | 6
| 1 | 24th floor checking | 2
| 2 | 4th floor GLD wiring | 2
| 3 | 28th floor fa points | 2
| 4 | 2nd floor corridor wiring | 2
| 5 | 4th floor LP marking | 2
|  | Man power | 10
| 1 | 31st floor tagging | 2
| 2 | 5th floor GLD Wiring | 2
| 3 | 2nd floor corridor wiring | 2
| 4 | 503 LP marking | 2
|  | Man power | 8
| 1 | 2402&2403 checking | 2
| 2 | 2nd floor corridor wiring | 2
| 3 | 503 LP marking | 2
|  | Man power | 6
| 1 | 25th floor checking | 2
| 2 | 5th floor GLD Wiring | 2
| 3 | 503 LP marking | 2
|  | Man power | 6
| 1 | 3101&3102 tagging | 2
|  | Man power | 2
| 1 | 22nd floor snag points | 2
| 2 | 8th floor GLD Wiring | 2
| 3 | 6th floor LP marking | 2
|  | Man power | 6
| 1 | 22nd floor snag points | 2
| 2 | 4th floor snag points | 2
| 3 | 6th floor LP marking | 2
|  | Man power | 6
| 1 | 25th floor snag points | 2
| 2 | 4th loor snag points | 2
| 3 | 6th floor LP marking | 3
| 4 | 32nd floor wiring | 2
| 5 | 25th &26 floor footlamp cutting chepping | 2
| 6 | 2nd MEADB | 2
|  | Man power | 13
| z | 25th floor snag points | 2
| 2 | 4th loor snag points | 2
| 3 | 6th floor LP marking | 2
| 4 | 27th floor checking | 2
| 5 | 25th &26 floor footlamp cutting chepping | 2
| 6 | 2nd MEADB | 2
|  | Man power | 12
| 1 | 7th floor LP marking | 2
| 2 | 27th floor checking | 2
| 3 | 25th &26 floor footlamp cutting chepping | 2
| 4 | 2nd MEADB | 1
|  | Man power | 5
| 1 | 7th floor marking LP | 3
| 2 | ODU connection | 1
| 3 | earth strip power | 1
|  | Man power | 5
| 1 | 8th floor marking LP | 3
| 2 | MAEDB instalation | 6
|  | Man power | 9
| 1 | 2nd floor MAEDB Dressing | 4
| 2 | 9th floor Lp marking | 2
| 3 | 25th floor snag points | 2
|  | Man power | 8
| 1 | 2nd floor MAEDB Dressing | 4
| 2 | 9th floor Lp marking | 3
| 3 | 26th floor snag points | 2
|  | Man power | 9
| 1 | 2nd floor MAEDB Dressing | 4
| 2 | 9th floor Lp marking | 3
| 3 | 26th floor snag points | 2
|  | Man power | 9
| 1 | 2nd floor MAEDB Dressing | 2
| 2 | 2nd floor corridor | 2
| 3 | 32 floor wiring | 2
|  | Man power | 6
| 1 | 25th floor snag points | 2
| 2 | 7th and 8th floor LP snag points | 2
| 3 | 3rd floor Ac socket fixing | 1
|  | Man power | 5
| 1 | 32nd floor wiring | 2
| 2 | 2nd floor corridor | 1
|  | Man power | 3
| 1 | 32nd floor wiring | 2
|  | Man power | 2
| 1 | 32nd floor flexible and dummy fixing | 2
|  | Man power | 2
| 1 | 32nd floor wiring | 2
| 2 | 2nd floor corridor | 1
|  | Man power | 2
| 1 | 27th floor checking | 2
| 2 | 2nd floor corridor | 1
|  | Man power | 3
| 1 | 27th floor checking | 2
| 2 | 2nd floor corridor | 3
|  | Man power | 5
| 1 | 27th floor checking | 2
| 2 | 9th and 8th floor LP marking | 2
| 3 | lift -2 | 2
|  | Man power | 6
| 1 | 27th floor checking | 2
| 2 | 12th floor checking | 2
| 3 | lift -2 | 2
|  | Man power | 6
| 1 | 27th floor checking | 2
| 2 | 15th floor marking | 2
| 3 | lift -2 | 2
|  | Man power | 6
| 1 | 2nd floor corridor Lp marking | 1
| 2 | lift -2 | 2
|  | Man power | 3
| 1 | 2nd floor corridor Lp marking | 1
| 2 | lift -2 | 3
|  | Man power | 4
| 1 | 27th floor checking | 2
| 2 | 2nd floor corridor | 2
| 3 | lift -2 | 3
|  | Man power | 7
| 1 | staircase checking | 1
| 2 | lift -2 | 3
|  | Man power | 4
| 1 | Earth strip laying | 1
| 2 | 2nd floor corridor | 2
| 3 | 6th floor Ac socket fixing | 3
|  | Man power | 5
| 1 | Earth strip laying | 1
| 2 | 6th floor Ac socket fixing | 2
|  | Man power | 3
| 1 | Earth strip laying | 1
| 2 | 8th floor Ac socket fixing | 2
|  | Man power | 3
| 1 | GLD wiring | 1
| 2 | 13th floor footlamp fixing | 1
|  | Man power | 2
| 1 | 2nd floor | 1
| 2 | RO conduit | 1
|  | Man power | 2
| 1 | 27th floor cutting chepping | 2
| 2 | 301 switch board | 2
|  | Man power | 4
| 1 | 27th floor cutting chepping | 2
|  | Man power | 2
| 1 | 28th floor cutting chepping | 4
| 2 | 301 switch board | 2
|  | Man power | 6
| 1 | 301 switch board | 2
|  | Man power | 2
| 1 | 32th floor cutting chepping | 2
| 2 | 303 ferrol & box cleaning | 4
|  | Man power | 6
| 1 | 303 ferrol & box cleaning | 2
| 2 | 3rd floor corridor | 2
| 3 | 303 ferrol & box cleaning | 2
| 4 | 29th floor checking | 2
|  | Man power | 8
| 1 | 30th floor cutting chepping | 2
| 2 | 3rd floor corridor | 2
| 3 | 303 ferrol & box cleaning | 2
|  | Man power | 6
| 1 | 301 switch board fixing | 2
|  | Man power | 2
| 1 | 303 Switch Board fixing | 2
| 2 | 3rd floor corridor wiring | 2
| 3 | 4th floor corridor wiring | 2
| 4 | 5th floor corridor wiring | 2
| 5 | Earth strip laying | 2
|  | Man Power | 10
| 1 | 303 Switch Board fixing | 2
| 2 | 3rd floor corridor wiring | 2
| 3 | 4th floor corridor wiring | 1
| 4 | 27th floor snag points | 2
| 5 | Earth strip laying | 1
|  | Man Power | 8
| 1 | 303 Switch Board fixing | 2
| 2 | 3rd floor corridor wiring | 2
| 3 | 4th floor corridor wiring | 1
| 4 | 27th floor snag points | 2
|  | Man Power | 7
| 1 | 302 AEDB dressing | 2 | AEDB Ferrules WIP
| 2 | 7th floor corridor wiring | 2 | Not engaged | Manpower Shited to 403 Theft Circuit Laying
| 3 | External LPS Conductor Laying | 1 | Completd
|  | Man Power | 5
| 1 | 302 AEDB dressing | 1 | AEDB Ferrules WIP |  | 1503 Slab Monitoring Worker | 1
| 2 | 7th floor corridor wiring | 2 | Not engaged | Manpower Shited to 403 Theft Circuit Laying | 1601 Box fixing &Wall | 3
| 3 | 28th floor snag points | 2 | Completd |  | 1602 Wall | 3
|  | Man Power | 5 |  |  | Man Power | 5
| 1 | 302 AEDB dressing | 1 | Not engaged | Man power shifted to 303 Box fixing | 1601 Wall & Slab | 5
| 2 | 4th floor corridor wiring | 2 | Completd |  | 1602 Wall | 2
| 3 | 26th floor snag points | 2 | WIP 50%
|  | Man Power | 5 |  |  | Man Power | 7
| 1 | 302 switch Board | 2 | WIP (60% -completed) |  | 1601 Wall & Slab | 1
| 2 | 7th floor corridor wiring | 2 | WIP (80%-completed) |  | 1602 Wall | 6
| 3 | 26th floor snag points | 2 | completd
|  | Man Power | 6 |  |  | Man Power | 7
20-11-2025 | 1 | 1st floor wiring | 2 | WIP (60% -completed) |  | 1603 wall conduit | 2
| 2 | 8th floor corridor wiring | 4 | WIP (10%-completed) |  | 1701 BOX fixing | 3
| 3 | 6th floor corridor wiring | 2 | WIP (10% - completed) |  | Material Packing | 2
|  | Man Power | 8 |  |  | Man Power | 7
21-11-2025 | 1 | 1st floor wiring | 2 | WIP (70% -completed) |  | 1603 wall conduit slab | 5
| 2 | 8th floor corridor wiring | 2 | WIP (10%-completed) |  | 1602 screw open & 1701 Bax fixing | 2
| 3 | 401 ferrol fixing | 2 | WIP (30% -completed)
| 4 | 5th floor corridor wiring | 2 | completed
|  | Man Power | 8 |  |  | Man Power | 7
22-11-2025 | 1 | 1st floor wiring | 2 | WIP (80% -completed) |  | 1603 wall conduit slab & 1701 Wall | 5
| 2 | 6th floor corridor wiring | 2 | WIP (20%-completed) |  | 1702 Bax fixing | 2
| 3 | 401 ferrol fixing | 2 | WIP (30% -completed) |  | 701 thread pulling | 3
|  | Man Power | 6 |  |  | Man Power | 10
24-11-2025 | 1 | foot lamp marking | 1 | WIP (13th floor working ) |  | 1701 Wall & slab | 6
| 2 | 29 th floor Wiring snag points | 2 | wip |  | 1702 Wall conduit | 2
| 3 | 401 ferrol fixing | 2 | WIP (50% -completed) |  | 1703 Box fixing | 2
| 4 | 5th floor corridor wiring | 2 | completed (Unit 3 pending)
|  | Man Power | 7 |  |  | Man Power | 10
25-11-2025 | 1 | 1st floor wiring | 2 | WIP (80% completed ) |  | 1701 Slab corridor | 2
| 2 | 29 th floor Wiring snag points | 2 | wip (28th floor working ) |  | 1702wall conduit | 2
| 3 | 401 ferrol fixing | 1 | WIP (50% -completed) |  | 6th floor corridor thread pulling | 2
| 4 | 6th floor corridor wiring | 2 | WIP (60% - completed) |  | 1703 Box fixing & wall | 3
|  | Man Power | 7 |  |  | Man Power | 9
26-11-2025 | 1 | 1st floor wiring | 2 | WIP (80% completed ) |  | 1703 wall conduit | 2
| 2 | 3rd floor 302 Switch board fixing | 2 | WIP (50% -completed) |  | 1702 wall & slab | 6
| 3 | Earth strip laying | 1 | completed |  | 6th floor corridor thread pulling | 2
|  | Man Power | 5 |  |  | Man Power | 10

## Finishings Tracker
Unit No | Flat Internal | [10 empty] | Corridor
| Till board Closing |  | Till 1st Coat Clearance |  |  |  |  | Till 2nd Coat Clearance |  |  |  | Till board Closing |  | Till 1st Coat Clearance |  |  |  |  | Till 2nd Coat Clearance
| Wiring QC Check Dt. | HO For Board Closing | Light Marking QC Check Dt. | HO to Civil for Cutting | Light Cutting Completion Dt. | Cutting Post Check Dt. | Frame Rectification Dt. | Ho to Civil for 1st Coat | 1st coat Completion& HO MEP | Fixtures Installation Qc chek Dt. | HO For Send Coat | Wiring QC Check Dt. | HO For Board Closing | Marking QC Check Dt. | HO to Civil for Cutting | Light Cutting Completion Dt. | Cutting Post Check Dt. | Frame Rectification Dt. | Ho to Civil for 1st Coat | 1st coat Completion& HO MEP | Fixtures Installation Qc chek Dt. | HO For Send Coat
101
102
103
201 | Completed | 1-18-2025 | [9 empty] | 9-15-2025
202
203
301 | Completed | 1-31-2025 | [9 empty] | 2025-10-11
302
303
401 | Completed | 2025-03-02 | [9 empty] | 2025-12-11
402
403
501 | Completed | 2-17-2025 | [9 empty] | 11-19-2025
502
503
601 | Completed | 2-27-2025 | [9 empty] | 12-15-2025
602
603
701 | Completed | 3-13-2025 | [9 empty] | 2025-12-12
702
703
801 | Completed | 23-24-2025 | [9 empty] | 12-20-2025
802
803
901 | Completed | 3-27-2025 | [9 empty] | 12-22-2025
902
903
1001 | Completed | 2025-06-04 | [9 empty] | 12-22-2025
1002
1003
1101 | Completed | 4-20-2025 | [9 empty] | 12-25-2026
1102
1103
1201 | Completed | 4-20-2025 | [9 empty] | 2026-05-01
1202
1203
1301 | Completed | 2-27-2025 | [9 empty] | 2026-11-01
1302
1303
1401 | Completed | 2-27-2025 | [9 empty] | 2026-11-01
1402
1403
1501 | Completed | 2-27-2025 | [9 empty] | 2026-11-01
1502
1503
1601 | Completed | 2-27-2025 | [9 empty] | 2026-11-01
1602
1603
1701 | Completed | 2-27-2025 | [9 empty] | 2026-11-01
1702
1703
1801 | Completed | 2-27-2025 | [9 empty] | 2026-11-01
1802
1803
1901 | Completed | 2-27-2025 | [9 empty] | 1-16-2026
1902
1903
2001 | Completed | 2-27-2025 | [9 empty] | 1-16-2026
2002
2003
2101 | Completed | 2-27-2025 | [9 empty] | 1-19-2026
2102
2103
2201 | Completed | 2-27-2025 | [9 empty] | 1-19-2026
2202
2203
2301 | Completed | 2-27-2025 | [9 empty] | 1-23-2026
2302
2303
2401 | Completed | 2-27-2025 | [9 empty] | 1-23-2026
2402
2403
2501 | Completed | 2-27-2025 | [9 empty] | 1-29-2026
2502
2503
2601 | Completed | 2-27-2025 | [9 empty] | 1-29-2026
2602
2603
2701 | Completed | 2-27-2025 | [9 empty] | 1-29-2026
2702
2703
2801 | Completed | [10 empty] | 1-29-2026
2802
2803
2901 | Completed | [10 empty] | 2026-02-02
2902
2903
3001 | Completed | [10 empty] | 2026-02-02
3002
3003
3101 | Completed | [10 empty] | 2026-02-02
3102
3103
3201 | Completed
3202
3203

## Clearances
List of Activitys Related to Fire NOC -20-12-2025
Sl.No | Activity | Status | [31 empty] | Huddles
I. | Tower Internal Electrical | 1st | 2nd | 3rd | 4th | 5th | 6th | 7th | 8th | 9th | 10th | 11th | 12th | 13th | 14th | 15th | 16th | 17th | 18th | 19th | 20th | 21st | 22nd | 23rd | 24th | 25th | 26th | 27th | 28th | 29th | 30th | 31st | 32nd | -
1 | Corridor Wiring | [32 empty] | -
2 | FA | [32 empty] | FA Fixtures to be Supplied
3 | PA | [32 empty] | PA Fixtures to be Supplied
4 | ETBS | [32 empty] | Fixtures to be supplied
5 | S/B | [32 empty] | -
6 | Staircase Wiring | [32 empty] | Circuit Wiring Pending
II. | External Electrical | Stilt Level | [7 empty] | Basement -1 | [7 empty] | Basement -2 | [7 empty] | Basement -3
7 | FCC Room (Cable Tray, FA PA Cabling & Panels) | [8 empty] | - | [7 empty] | - | [7 empty] | - | [7 empty] | Panels yet to be finalised
8 | Fire Pump Room (Cable tray, Cabling, Panel& Earthing) | - | [31 empty] | Cable Schedule Needed& Earth Studs not Available
9 | Basement Ventilation System( Tray& Panels, Cabling) | - | [31 empty] | Ventilation Panels& FS Cables Not Received
10 | Tower Electrical Rooms ( Tray& Panels, Cabling) | - | [31 empty] | CSP Panel
11 | Ventilation syatem Cable Tray | - | [31 empty] | -
12 | Electrical Tray (For Above Services) | - | [31 empty] | Stores& Floor level clearance needed
13 | Staircase& Lobby Pressurization (Tray& Panel, Cabling) | - | [31 empty] | Trays& Panels Not Received
14 | Service Lift Charging | - | [31 empty] | Earth Studs Not Found in Shaft

## Sheet1
Common area Lighting
Staircase Lighting