## Tower -B
Activity Tracker Tower -B/E As on Dt. 21-01-2026
Contractor : Dayakar electricals
Critical Issues
1 | Wire Material Shortage (10.0Sqmm, 6.0Sqmm, 4.0Sqmm& Cat6 Cable) - Hindrance to 1st Coat Paint Clearance& Common area Board Closing Clearance
2 | Delay in Giving Light marking at Toilets& Utilitys - Hindrance 1st Coat Paint
3 | Quality Deviation For Switch Boards Eraction Works - Average of 30 snag points per each unit
4 | Delay in Phase -2 Conduit Post checkings. { 23rd Floor Structure WIP - Post Checking still 10th Floor WIP}
Sl.No | Activity | Date of Clearance Given | Planned/ Committed Completion Date | Qc Checking Date | Actual Completion Date | Days of Delay | Remarks
I. | Common area Board Closing Clearance :
1 | 3rd Floor Corridor | 2025-10-30 | 2025-11-01 | 2025-11-10 | 2025-11-10 | 9
2 | 4th Floor Corridor | 2025-10-30 | 2025-11-03 | 2025-11-12 | 2025-11-12 | 9
3 | 5th Floor Corridor | 2025-10-30 | 2025-11-05 | 2025-11-19 | 2025-11-20 | 15
4 | 6th Floor Corridor | 2025-10-30 | 2025-11-07 | 2025-12-15 | 2025-12-15 | 38
5 | 7th Floor Corridor | 2025-10-30 | 2025-11-09 | 2025-12-12 | 2025-12-13 | 34
6 | 8th Floor Corrdor | 2025-10-30 | 2025-11-11 | 2025-12-20 | 2025-12-22 | 41
7 | 9th Floor Corrdor | 2025-10-30 | 2025-11-13 | 2025-12-22 | 2025-12-23 | 40
8 | 10th Floor Corrdor | 2025-10-30 | 2025-11-15 | 2025-12-22 | 2025-12-26 | 41
9 | 11th Floor Corrdor | 2025-10-30 | 2025-11-17 | 2025-12-25 | 2025-12-26 | 39
10 | 12th Floor Corrdor | 2025-10-30 | 2025-11-19 | 2025-12-25 | 2025-12-26 | 37
11 | 13th Floor Corrdor | 2025-10-30 | 2025-11-21 | 2026-01-05 | 2026-01-06 | 46
12 | 14th Floor Corrdor | 2025-10-30 | 2025-11-23 | 2026-01-11 | 2026-01-12 | 50
13 | 15th Floor Corrdor | 2025-10-30 | 2025-11-25 | 2026-01-11 | 2026-01-12 | 48
14 | 16th Floor Corrdor | 2025-10-30 | 2025-11-27 | 2026-01-11 | 2026-01-12 | 46
15 | 17th Floor Corrdor | 2025-10-30 | 2025-11-29 | 2026-01-11 | 2026-01-12 | 44 | Unit -3 6.0 Sqmm ODU Cabling Pending Due to Material Shortage
16 | 18th Floor Corrdor | 2025-10-30 | 2025-12-01 | 2026-01-11 | 2026-01-12 | 42 | Unit -3 6.0 Sqmm ODU Cabling Pending Due to Material Shortage
17 | 19th Floor Corrdor | 2025-10-30 | 2025-12-03 | 2026-01-16 | 2026-01-17 | 45 | 6.0 Sqmm ODU Cabling Pending Due to Material Shortage
18 | 20th Floor Corrdor | 2025-10-30 | 2025-12-05 | 2026-01-16 | 2026-01-17 | 43 | 6.0 Sqmm ODU Cabling Pending Due to Material Shortage
19 | 21st Floor Corrdor | 2025-10-30 | 2025-12-07 | 2026-01-19 | 2026-01-20 | 44 | 6.0 Sqmm, 10.0 Sqmm Cabling Pending Due to Material Shortage
20 | 22nd Floor Corrdor | 2025-10-30 | 2025-12-09 | 2026-01-19 | 2026-01-20 | 42 | 6.0 Sqmm, 10.0 Sqmm Cabling Pending Due to Material Shortage
21 | 23rd Floor Corrdor | 2025-10-30 | 2025-12-11 | - | - | - | WIP
22 | 24th Floor Corrdor | 2025-10-30 | 2025-12-13 | - | - | - | WIP
23 | 25th Floor Corrdor | 2025-10-30 | 2025-12-15 | - | - | - | WIP
24 | 26th Floor Corrdor | 2025-10-30 | 2025-12-17 | - | - | - | WIP
25 | 27th Floor Corrdor | 2025-10-30 | 2025-12-19 | - | - | - | WIP
26 | 28th Floor Corrdor | 2025-10-30 | 2025-12-21 | - | - | - | WIP
27 | 29th Floor Corrdor | 2025-10-30 | 2025-12-23 | - | - | - | WIP
28 | 30th Floor Corrdor | 2025-10-30 | 2025-12-25 | - | - | - | WIP
29 | 31st Floor Corrdor | 2025-10-30 | 2025-12-27 | - | - | - | WIP
30 | 32nd Floor Corrdor | 2025-10-30 | 2025-12-29 | - | - | - | WIP
II. | Staircase Circuit Wiring
1 | Fire Staircase | 2025-10-30 | 2025-11-06 | - | - | - | WIP
2 | General Staircase | 2025-10-30 | 2025-11-06 | - | - | - | WIP
III. | Switboards& Light Fixtures Eraction :
1 | Unit -301 | 2025-10-28 | 2025-10-31 | 2025-11-03 | 2025-11-03 | 3
2 | Unit -302 | 2025-11-17 | 2025-11-20 | 2025-11-24 | 2025-11-25 | 5
3 | Unit -303 | 2025-10-31 | 2025-11-03 | 2025-11-11 | 2025-11-11 | 8
4 | Unit -401 | 2025-11-26 | 2025-11-29 | 2025-12-08 | 2025-12-11 | 12
5 | Unit -402 | 2025-12-01 | 2025-12-04 | 2025-12-08 | 2025-12-12 | 8
6 | Unit -403 | 2025-12-03 | 2025-12-06 | 2025-12-08 | 2025-12-13 | 7
7 | Unit -601 | 2025-12-12 | 2025-12-15 | 2025-12-20 | 2026-01-05 | 21
8 | Unit -602 | 2025-12-17 | 2025-12-20 | 2026-01-06 | - | - | Work in Progress ( Snag Points -Avg 30 No's/ Flat)
9 | Unit -603 | 2026-01-18 | 2026-01-21 | - | - | - | Work in Progress
10 | Unit -701 | 2026-01-06 | 2026-01-09 | - | - | - | Work in Progress
11 | Unit -702 | 2025-12-27 | 2025-12-30 | 2026-01-20 | - | - | Work in Progress ( Snag Points -Avg 30 No's/ Flat)
12 | Unit -703 | 2025-12-27 | 2025-12-30 | 2026-01-20 | - | - | Work in Progress ( Snag Points -Avg 30 No's/ Flat)
13 | Unit -701 | 2026-01-18 | 2026-01-21 | - | - | - | Work in Progress
IV. | MAEDB Installation& Terminations :
1 | Unit -301 | 2025-11-20 | 2025-11-22 | - | WIP | - | DB Fixing Completed, Dressing Pending
2 | Unit -302 | 2025-11-20 | 2025-11-24 | - | WIP | - | DB Fixing& Dressing Completed, Terminations WIP
3 | Unit -303 | 2025-11-20 | 2025-11-26 | - | WIP | - | DB Fixing& Dressing Completed, Terminations WIP
4 | Unit -401 | 2025-11-20 | 2025-11-28 | - | WIP | - | DB Fixing completed, Dressing WIP
5 | Unit -402 | 2025-11-20 | 2025-11-30 | - | WIP | - | DB Fixing completed, Dressing WIP
6 | Unit -403 | 2025-11-20 | 2025-12-02 | - | WIP | - | DB Fixing completed, Dressing WIP
7 | Unit -601 | 2025-11-20 | 2025-12-04 | - | WIP | - | DB Fixing Completed, Dressing Pending
8 | Unit -602 | 2025-11-20 | 2025-12-06 | - | WIP | - | DB Fixing Completed, Dressing Pending
9 | Unit -603 | 2025-11-20 | 2025-12-08 | - | WIP | - | DB Fixing Completed, Dressing Pending
10 | Unit -701 | 2025-11-20 | 2025-12-10 | - | WIP | - | No Clearance
11 | Unit -702 | 2025-11-20 | 2025-12-12 | - | WIP | - | DB Fixing Completed, Dressing Pending
12 | Unit -703 | 2025-11-20 | 2025-12-14 | - | WIP | - | DB Fixing Completed, Dressing Pending
13 | Unit -801 | 2025-11-20 | 2025-12-16 | - | WIP | - | DB Fixing Completed, Dressing Pending
14 | Unit -802 | 2025-11-20 | 2025-12-18 | - | WIP | - | DB Fixing Completed, Dressing Pending
15 | Unit -803 | 2025-11-20 | 2025-12-20 | - | WIP | - | DB Fixing Completed, Dressing Pending
V. | Flat Internal Board Closing :
| Floor |  |  | QC Check Dt. | Snag Completion Dt. | Delay (Days)
1 | 27th Floor |  |  | 2025-10-30 | 2025-11-19 | 20
2 | 28th Floor |  |  | 2025-11-03 | 2026-01-08 | 66 | Few Snags Still Pending
3 | 29th Floor |  |  | 2025-11-05 | 2026-01-08 | 64 | Few Snags Still Pending
4 | 30th Floor |  |  | - | - | - | Continuity Checking Pending
5 | 31st Floor |  |  | - | - | - | Continuity Checking Pending
6 | 32nd Floor |  |  | - | - | - | Continuity Checking Pending
Formulas:
Planned/ Committed Completion Date = [Date of Clearance Given]+2
Planned/ Committed Completion Date = [Planned/ Committed Completion Date, row above]+2

## T-B Manpower Details
Tower -B Manpower Details
Contractor : Dayakar Electricals
Sl.No | List Of Activitys | Present Manpower Requirement ( No's ) | 2025-11-01 | [29 empty] | 2025-12-01 | [30 empty] | 2026-01-01
 | time axis 2025-11-01 to 2026-03-26
1 | Common Area Wiring (upto 14th Floor) |  | 2025-11-03: 2; 2025-11-05: 2; 2025-11-06: 2; 2025-11-09: 6; 2025-11-10: 3; 2025-11-11: 3; 2025-11-13: 2; 2025-11-14: 2; 2025-11-15: 2; 2025-11-17: 2; 2025-11-18: 2; 2025-11-19: 4; 2025-11-21: 4; 2025-11-22: 2; 2025-11-25: 2; 2025-11-27: 2; 2025-11-28: 2; 2025-11-29: 2; 2025-12-01: 2; 2025-12-06: 2; 2025-12-07: 2; 2025-12-09: 2; 2025-12-11: 2; 2025-12-12: 2; 2025-12-13: 4; 2025-12-15: 2; 2025-12-16: 2; 2025-12-17: 4; 2025-12-18: 6; 2025-12-19: 4; 2025-12-20: 6; 2025-12-21: 6; 2025-12-22: 6; 2025-12-23: 6; 2025-12-24: 5; 2025-12-25: 6; 2025-12-26: 6; 2025-12-27: 6; 2025-12-28: 6; 2025-12-29: 5; 2025-12-30: 5; 2025-12-31: 6; 2026-01-02: 6; 2026-01-03: 6; 2026-01-05: 6; 2026-01-06: 6; 2026-01-07: 6
2 | Common Area Wiring (15th floor & Above) | 4 | 2026-01-08: 6; 2026-01-09: 6; 2026-01-10: 6; 2026-01-11: 6; 2026-01-12: 6; 2026-01-13: 6; 2026-01-14: 6; 2026-01-16: 6; 2026-01-17: 6; 2026-01-18: 6; 2026-01-19: 6; 2026-01-20: 6; 2026-01-21: 6; 2026-01-22: 6; 2026-01-24: 6; 2026-01-28: 6; 2026-01-29: 6; 2026-01-30: 6; 2026-01-31: 4; 2026-02-01: 4; 2026-02-02: 4; 2026-02-03: 4; 2026-02-04: 4; 2026-02-05: 4; 2026-02-06: 4; 2026-02-07: 4; 2026-02-08: 4; 2026-02-09: 4; 2026-02-10: 4; 2026-02-11: 4; 2026-02-12: 4; 2026-02-23: 2; 2026-03-01: 2; 2026-03-02: 4; 2026-03-03: 4; 2026-03-06: 4; 2026-03-07: 2; 2026-03-08: 1; 2026-03-09: 3; 2026-03-11: 2; 2026-03-12: 2; 2026-03-13: 2; 2026-03-21: NO Man powere
3 | Switch Boards Eraction | 4 | 2 |  | 4 | 4 | 4 | 2 | 2 |  | 2 | 2 | 2 |  | 2 | 1 | 1 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 |  | 1 | 2 | 2 | 1 | 1 |  | 3 | 3 | 4 | 6 | 3 | 3 | 2 | 3 | 3 | 3 | 2 | 2 | 4 |  | 2 | 2 | 3 | 4 | 2 | 3 | 3 | 4 | 4 | 3 | 2 | 2 | 4 | 5 | 4 | 4 | 4 |  | 4 | 4 |  | 5 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 3 | 3 | 4 | 4 | 4 | 4 |  | 3 |  |  |  | 3 | 2 | 3 | 4 | 3 | 2 | 2 |  | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 |  | 4 | 4 | 7 | 7 | 6 | 4 | 2 | 2 |  | 2 | 2 | 5 | 6 | 3 | 4 | 5 | 4 | 2 | 2 | 2 | 3 | 2 | 4 | 2 | 2 |  |  | 5 | 3 | 3
4 | MAEDB Installation (informed to start on 20-11-25) | 2 | 2025-11-28: 2; 2025-11-29: 2; 2025-12-11: 2; 2025-12-12: 2; 2025-12-15: 2; 2025-12-16: 2; 2025-12-17: 2; 2025-12-27: 2; 2026-01-06: 1; 2026-01-07: 1; 2026-01-08: 1; 2026-01-09: 1; 2026-01-10: 1; 2026-01-11: 1; 2026-01-12: 1; 2026-01-13: 1; 2026-01-14: 1; 2026-01-15: 1; 2026-01-17: 1; 2026-01-18: 1; 2026-01-24: 2; 2026-01-29: 2; 2026-02-02: 1; 2026-02-03: 1; 2026-02-05: 1; 2026-02-06: 1; 2026-02-07: 1; 2026-02-08: 1; 2026-02-09: 1; 2026-02-10: 1; 2026-02-11: 1; 2026-02-12: 1; 2026-02-13: 1; 2026-02-14: 1; 2026-02-15: 1; 2026-02-16: 1; 2026-02-17: 1; 2026-02-18: 1; 2026-02-19: 1; 2026-02-20: 1; 2026-02-28: 2; 2026-03-01: 2; 2026-03-02: 2; 2026-03-03: 2; 2026-03-05: 1; 2026-03-06: 1; 2026-03-10: 2; 2026-03-15: 1; 2026-03-18: 1
5 | Internal Flase ceiling Clearance | 2 | 2025-11-03: 4; 2025-11-04: 2; 2025-11-05: 2; 2025-11-06: 2; 2025-11-10: 2; 2025-11-11: 2; 2025-11-14: 2; 2025-11-15: 2; 2025-11-17: 2; 2025-11-18: 2; 2025-11-19: 2; 2025-11-25: 2; 2025-11-28: 2; 2025-12-25: 4; 2025-12-29: 2; 2025-12-30: 2; 2025-12-31: 2; 2026-01-03: 2; 2026-01-19: 2
6 | Staircase Circuit Wiring | 2 | 2026-01-11: 2; 2026-01-12: 2; 2026-01-24: 2; 2026-01-28: 2; 2026-02-12: 2; 2026-02-13: 2
7 | 1st Floor Wiring |  | 2025-11-18: 2; 2025-11-19: 2; 2025-11-21: 2; 2025-11-22: 2; 2025-11-25: 2; 2025-11-26: 2; 2025-11-27: 2; 2025-11-28: 2; 2025-12-01: 2; 2025-12-02: 2; 2025-12-03: 2; 2025-12-15: 2; 2025-12-16: 2
8 | AEDB Alignment & Plaster Clearans | 1 | 2026-01-20: 2; 2026-01-21: 2; 2026-02-28: 2; 2026-03-14: 1; 2026-03-15: 2; 2026-03-16: 2; 2026-03-17: 2; 2026-03-25: 1
9 | Planter Footlamp back box Fixing& Alignment | 1 | 2025-11-23: 1; 2025-12-06: 1; 2025-12-08: 2; 2025-12-09: 2; 2025-12-10: 1; 2025-12-28: 2; 2025-12-29: 2; 2025-12-30: 2; 2026-01-03: 1; 2026-01-10: 2; 2026-01-11: 2; 2026-01-12: 2; 2026-01-20: 2; 2026-01-21: 2; 2026-01-24: 2; 2026-01-28: 2
10 | Theft Circuits Laying | 2 | 2025-12-03: 2; 2025-12-04: 2; 2025-12-05: 4; 2025-12-06: 4; 2025-12-08: 2; 2025-12-09: 2; 2025-12-10: 2; 2025-12-20: 2; 2025-12-21: 2; 2026-01-05: 2; 2026-01-06: 2; 2026-01-07: 2; 2026-01-08: 2; 2026-01-14: 2; 2026-01-16: 2; 2026-01-18: 2; 2026-01-30: 2; 2026-01-31: 2; 2026-02-03: 3; 2026-02-05: 2; 2026-02-07: 2; 2026-02-13: 3; 2026-02-14: 3; 2026-02-15: 3; 2026-02-17: 3; 2026-02-18: 4; 2026-03-01: 2; 2026-03-02: 2; 2026-03-05: 2
11 | Misclaneous Works Below : | 2 | 2026-01-29: 2; 2026-02-10: 4; 2026-02-11: 4; 2026-02-14: 2; 2026-02-15: 4; 2026-02-16: 2; 2026-02-22: 2; 2026-02-23: 2; 2026-03-03: 2; 2026-03-05: 2; 2026-03-06: 2; 2026-03-07: 2; 2026-03-08: 2; 2026-03-13: 2; 2026-03-14: 3; 2026-03-16: 2; 2026-03-17: 2; 2026-03-18: 2; 2026-03-23: 2; 2026-03-25: 1
12 | Light Marking |  | 2026-01-09: 2; 2026-01-10: 2
13 | External LPS Conductor Laying | - | 2025-11-09: 2; 2025-11-10: 1; 2025-11-13: 1; 2025-11-23: 2; 2025-11-26: 1; 2026-01-14: 1; 2026-01-17: 1; 2026-03-06: 1
14 | Basement Wall Conduit | - | 2025-11-27: 1; 2026-02-01: 2; 2026-02-02: 2; 2026-02-09: 2; 2026-02-11: 2; 2026-02-12: 2; 2026-02-13: 2; 2026-02-14: 2
15 | Flat Continuity | 0 | 2026-01-22: 2; 2026-01-29: 2; 2026-01-30: 2; 2026-02-03: 2; 2026-02-06: 2; 2026-02-12: 2; 2026-03-22: 2
16 | Lifts Pending Works | - | 2025-11-23: 2; 2025-12-08: 2; 2025-12-12: 1; 2025-12-13: 1
Total Manpower |  | 20 | 2 | 0 | 10 | 6 | 8 | 6 | 2 | 0 | 10 | 8 | 7 | 0 | 5 | 5 | 5 | 2 | 6 | 8 | 10 | 0 | 8 | 6 | 7 | 0 | 7 | 5 | 7 | 9 | 5 | 0 | 7 | 5 | 8 | 8 | 7 | 10 | 4 | 9 | 9 | 6 | 6 | 7 | 9 | 0 | 8 | 8 | 9 | 10 | 6 | 11 | 11 | 10 | 10 | 8 | 12 | 8 | 12 | 13 | 13 | 13 | 12 |  | 10 | 13 | 0 | 13 | 13 | 13 | 13 | 12 | 14 | 14 | 14 | 10 | 13 | 4 | 8 | 11 | 12 | 12 | 14 | 14 | 14 |  | 15 |  |  |  | 15 | 14 | 13 | 10 | 9 | 11 | 12 | 4 | 10 | 10 | 10 | 8 | 10 | 12 | 12 | 12 | 10 | 11 | 11 | 8 | 7 | 8 | 4 | 4 | 4 | 6 | 4 | 4 | 4 | 7 | 7 | 10 | 12 | 10 | 10 |  | 7 | 10 | 9 | 10 | 6 | 6 | 7 | 6 | 6 | 6 | 5 | 7 | 6 | 7 | 2 | 2 | 0 | 2 | 7 | 3 | 6

## Tower-C
Works Delay Record Tower -C As on Dt. 26-11-2025
Contractor : Dayakar electricals
Sl.No | Activity | Date of Clearance Given | Planned/ Committed Completion Date | Actual Completion Date | Days of Delay | Remarks
I. | Switboards& Light Fixtures Eraction :
1 | Unit -301 | 2025-10-24 | 2025-10-27 | 2025-10-30 | 3
| Unit -302 | 2025-11-26 | 2025-10-29 | 2025-11-12 | 14
| Unit -303 | 2025-11-05 | 2025-11-08 | 2025-11-13 | 5
2 | Unit -501 | 2025-11-14 | 2025-11-17 | 2025-12-06 | 19
| Unit -502 | 2025-11-19 | 2025-11-22
| Unit -503 | 2025-11-23 | 2025-11-26
3 | Unit -402 | 2025-11-25 | 2025-11-28 | 2025-12-11 | 13
| Unit -403 | 2025-12-04 | 2025-12-07 | 2025-12-11 | 4
| Unit -401 | 2025-12-05 | 2025-12-08 | 2025-12-11 | 3
4 | Unit -603 | 2025-12-04 | 2025-12-07 | WIP
| Unit -601 | 2026-01-05 | 2026-01-08
| Unit -602 | 2026-01-04 | 2026-01-07
5 | Unit -701 | 2025-12-20 | 2025-12-23 | WIP
| Unit -703 | 2025-12-12 | 2025-12-15
| Unit -702 | 2025-12-16 | 2025-12-19
6 | Unit -901 | 2026-01-15 | 2026-01-18
| Unit -902 | 2026-01-19 | 2026-01-22
| Unit -903 | 2026-01-22 | 2026-01-25
7 | 1001 | 2025-12-24 | 2025-12-27
| 1002 | 2026-01-15 | 2026-01-18
1003
II. | MAEDB Installation& Terminations :
1 | 3rd Floor | 2025-11-20 | 2025-11-22 | WIP
2 | 5th Floor |  | 2025-11-24 | WIP
3 | 4th Floor |  |  | WIP
4 | 6th Floor
5 | 7th Floor
III. | Common area Board Closing :
1 | 3rd Floor Corridor | 2025-10-30 | 2025-11-01 | 2025-11-12 | 11
2 | 4th Floor Corridor | 2025-10-30 | 2025-11-03 | 2025-11-13 | 10
3 | 5th Floor Corridor | 2025-10-30 | 2025-11-05 | 2025-11-22 | 17
4 | 6th Floor Corridor | 2025-10-30 | 2025-11-07 | 2025-11-28 | 21
5 | 7th Floor Corridor | 2025-10-30 | 2025-11-09 | 2025-11-28 | 19
6 | 8th Floor Corrdor | 2025-10-30 | 2025-11-11 | 2025-12-13 | 32
7 | 9th Floor Corrdor | 2025-10-30 | 2025-11-13 | 2025-12-13 | 30
8 | 10th Floor Corrdor | 2025-10-30 | 2025-11-15 | 2025-12-18 | 33
9 | 11th Floor Corrdor | 2025-10-30 | 2025-11-17 | 2025-12-27 | 40
10 | 12th Floor Corrdor | 2025-10-30 | 2025-11-19 | 2025-12-24 | 35
11 | 13th Floor Corrdor | 2025-10-30 | 2025-11-21 | 2025-12-24 | 33
12 | 14th Floor Corrdor | 2025-10-30 | 2025-11-23 | 2025-12-27 | 34
13 | 15th Floor Corrdor | 2025-10-30 | 2025-11-25 | 2025-12-27 | 32
14 | 16th Floor Corrdor | 2025-10-30 | 2025-11-27 | 2026-01-05 | 39
15 | 17th Floor Corrdor | 2025-10-30 | 2025-11-29 | 2026-01-07 | 39
16 | 18th Floor Corrdor | 2025-10-30 | 2025-12-01 | 2026-01-06 | 36
17 | 19th Floor Corrdor | 2025-10-30 | 2025-12-03 | 2026-01-05 | 33
18 | 20th Floor Corrdor | 2025-10-30 | 2025-12-05 | 2026-01-05 | 31
19 | 21st Floor Corrdor | 2025-10-30 | 2025-12-07 | 2026-01-18 | 42 | cat-6 and ODU wiring pending
20 | 22nd Floor Corrdor | 2025-10-30 | 2025-12-09 | 2026-01-19 | 41 | cat-6 and ODU wiring pending
21 | 23rd Floor Corrdor | 2025-10-30 | 2025-12-11 | 2026-01-20 | 40 | cat-6 and ODU wiring pending
22 | 24th Floor Corrdor | 2025-10-30 | 2025-12-13
23 | 25th Floor Corrdor | 2025-10-30 | 2025-12-15
24 | 26th Floor Corrdor | 2025-10-30 | 2025-12-17
25 | 27th Floor Corrdor | 2025-10-30 | 2025-12-19
26 | 28th Floor Corrdor | 2025-10-30 | 2025-12-21
27 | 29th Floor Corrdor | 2025-10-30 | 2025-12-23
28 | 30th Floor Corrdor | 2025-10-30 | 2025-12-25
29 | 31st Floor Corrdor | 2025-10-30 | 2025-12-27
30 | 32nd Floor Corrdor | 2025-10-30 | 2025-12-29
IV. | Staircase Circuit Wiring
1 | Fire Staircase | 2025-10-30 | 2025-11-06 | Not Started |  | manpower not engaged yet
2 | General Staircase | 2025-10-30 | 2025-11-06 | Not Started |  | manpower not engaged yet
V. | Critical Issues
1 | Insufficient Manpower
4 | Staircase Circuit Wiring Not started till now in both towers ( Asper Commitments it is to be started by 25-10-2025. But Still Not Engaged.
5 | Phase -2 Conduit Post checkings.
Formulas:
Planned/ Committed Completion Date = [Date of Clearance Given]+3
Planned/ Committed Completion Date = [Planned/ Committed Completion Date, row above]+2

## T-C manpower details
Tower -C Manpower Details For The Month of Nov -2025.
Contractor : Dayakar Electricals
Sl.No | List Of Activitys | Present Manpower Requirement ( No's ) | November | [29 empty] | December | [30 empty] | January
 | time axis 2025-11-01 to 2026-03-22
1 | Common Area Wiring (upto 14th Floor) | 2 | 2025-11-01: 2; 2025-11-07: 2; 2025-11-08: 2; 2025-11-10: 2; 2025-11-11: 3; 2025-11-12: 2; 2025-11-13: 3; 2025-11-14: 2; 2025-11-15: 2; 2025-11-17: 4; 2025-11-18: 4; 2025-11-19: 4; 2025-11-20: 3; 2025-11-21: 2; 2025-11-22: 2; 2025-11-24: 2; 2025-11-25: 2; 2025-11-26: 2; 2025-11-27: 1; 2025-11-28: 2; 2025-11-29: 1; 2025-11-30: 1; 2025-12-01: 1; 2025-12-12: 2; 2025-12-13: 2; 2025-12-14: 2; 2025-12-16: 2; 2025-12-17: 2; 2025-12-18: 3; 2025-12-19: 4; 2025-12-20: 4; 2025-12-21: 3; 2025-12-22: 4; 2025-12-23: 4; 2025-12-24: 2; 2026-01-03: 4; 2026-01-04: 4; 2026-01-05: 2
2 | Common Area Wiring (15th floor & Above) | 2 | 2025-12-24: 2; 2025-12-25: 2; 2025-12-26: 4; 2025-12-27: 4; 2025-12-29: 5; 2025-12-30: 3; 2025-12-31: 4; 2026-01-10: 3; 2026-01-11: 3; 2026-01-12: 4; 2026-01-14: 4; 2026-01-16: 4; 2026-01-17: 4; 2026-01-22: 1; 2026-01-28: 1; 2026-01-29: 1; 2026-01-30: 5; 2026-01-31: 4; 2026-02-01: 5; 2026-02-02: 5; 2026-02-03: 1; 2026-02-04: 1; 2026-02-20: 2; 2026-02-21: 1; 2026-02-22: 1; 2026-03-01: 2; 2026-03-02: 3; 2026-03-03: 2; 2026-03-04: 2; 2026-03-05: 2; 2026-03-06: 3; 2026-03-07: 2
3 | Switch Boards Eraction | 4 | 2025-11-01: 2; 2025-11-03: 2; 2025-11-04: 4; 2025-11-05: 2; 2025-11-06: 5; 2025-11-07: 2; 2025-11-08: 4; 2025-11-10: 3; 2025-11-12: 2; 2025-11-13: 2; 2025-11-14: 2; 2025-11-21: 2; 2025-11-22: 2; 2025-11-24: 2; 2025-11-25: 2; 2025-11-26: 2; 2025-11-27: 5; 2025-11-28: 2; 2025-11-29: 4; 2025-11-30: 4; 2025-12-01: 4; 2025-12-02: 4; 2025-12-03: 2; 2025-12-04: 2; 2025-12-06: 1; 2025-12-07: 2; 2025-12-08: 2; 2025-12-09: 2; 2025-12-10: 5; 2025-12-11: 2; 2025-12-12: 2; 2025-12-13: 2; 2025-12-15: 2; 2025-12-16: 1; 2025-12-17: 1; 2025-12-26: 3; 2026-01-18: 3; 2026-01-19: 4; 2026-01-22: 2; 2026-01-23: 3; 2026-01-24: 3; 2026-01-27: 2; 2026-01-28: 4; 2026-01-29: 2; 2026-02-04: 3; 2026-02-05: 2; 2026-02-06: 4; 2026-02-07: 4; 2026-02-09: 2; 2026-02-10: 3; 2026-02-11: 4; 2026-02-12: 4; 2026-02-13: 4; 2026-02-14: 4; 2026-02-16: 4; 2026-02-17: 4; 2026-02-18: 4; 2026-02-19: 3; 2026-02-20: 2; 2026-02-21: 3; 2026-02-22: 1; 2026-02-23: 2; 2026-02-24: 2; 2026-02-26: 4; 2026-02-27: 5; 2026-02-28: 4
4 | Light fixtures installation |  | 2025-12-03: 3; 2025-12-04: 2; 2025-12-05: 1; 2025-12-06: 2; 2025-12-07: 1; 2025-12-08: 2; 2026-01-22: 2; 2026-01-23: 2; 2026-01-24: 2; 2026-01-27: 2; 2026-02-19: 1; 2026-02-21: 1; 2026-02-22: 1; 2026-02-23: 1; 2026-02-24: 1; 2026-03-05: 2; 2026-03-06: 2; 2026-03-08: 2
5 | MAEDB Installation (informed to start on 20-11-25) | 2 | 2025-11-29: 1; 2025-12-01: 1; 2025-12-11: 1; 2025-12-19: 1; 2025-12-20: 1; 2025-12-21: 1; 2025-12-22: 2; 2025-12-23: 1; 2025-12-24: 1; 2025-12-25: 3; 2025-12-27: 2; 2025-12-29: 2; 2025-12-30: 2; 2025-12-31: 2; 2026-01-06: 2; 2026-01-10: 1; 2026-01-17: 1; 2026-02-07: 1; 2026-02-09: 3; 2026-02-10: 2; 2026-02-11: 1; 2026-02-19: 1; 2026-02-20: 1; 2026-02-21: 1; 2026-03-02: 2; 2026-03-03: 2; 2026-03-04: 2; 2026-03-09: 3
6 | Internal Flase ceiling Clearance | 2 | 2025-11-14: 2; 2025-11-15: 2
7 | Staircase Circuit Wiring | 2 | 2025-12-17: 2; 2026-02-04: 2
8 | Planter Footlamp back box Fixing& Alignment | 1 | 2025-11-03: 2; 2025-11-24: 1; 2025-11-28: 2; 2025-12-03: 1; 2026-02-18: 2
9 | Misclaneous Works Below : | 2
| External LPS Conductor Laying | - | bar: 2025-11-01 to 2025-11-02; 2025-11-08; 2025-11-15; 2025-11-22; 2025-11-24 to 2025-11-25; 2025-11-27; 2025-11-29; 2025-12-06; 2025-12-09; 2025-12-12; 2025-12-28; 2026-01-02
| Basement Wall Conduit | - | 2026-02-05: 2; 2026-02-16: 2
| Lifts Pending Works | - | 2026-03-07: 2; 2026-03-08: 2; 2026-03-09: 2
| Light markings |  | 2025-12-02: 1; 2025-12-09: 1; 2025-12-11: 2; 2025-12-15: 2; 2025-12-17: 2; 2025-12-18: 2; 2026-01-29: 1
| FAPA conduit blockage rectification |  | 2025-12-24: 2; 2025-12-25: 2; 2025-12-26: 2; 2025-12-27: 2; 2025-12-29: 2; 2025-12-30: 2; 2026-01-02: 2; 2026-01-17: 2; 2026-01-19: 2; 2026-01-22: 2; 2026-01-24: 2; 2026-01-27: 2; 2026-01-29: 2; 2026-01-30: 2; 2026-01-31: 2; 2026-02-01: 2; 2026-02-03: 2; 2026-02-10: 2; 2026-02-11: 2; 2026-02-12: 2; 2026-02-13: 2
| AC units Socket installation |  | 2025-11-15: 1; 2025-12-02: 1; 2025-12-03: 1; 2025-12-04: 1; 2025-12-09: 1; 2025-12-11: 1; 2026-01-24: 2; 2026-03-03: 2
Total Manpower |  | 17 | 5 | 1 | 4 | 4 | 2 | 5 | 4 | 7 | 0 | 5 | 3 | 4 | 5 | 6 | 6 | 0 | 4 | 4 | 4 | 3 | 4 | 5 | 0 | 6 | 5 | 4 | 7 | 6 | 7 | 5 | 6 | 6 | 7 | 5 | 1 | 4 | 3 | 4 | 5 | 5 | 6 | 5 | 4 | 2 | 4 | 3 | 7 | 5 | 5 | 5 | 4 | 6 | 5 | 7 | 7 | 9 | 8 | 1 | 9 | 7 | 6 | 0 | 3 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 4 | 3 | 4 | 0 | 4 | 0 | 4 | 7 | 3 | 6 | 0 | 0 | 7 | 5 | 9 | 0 | 0 | 6 | 5 | 6 | 7 | 6 | 7 | 5 | 3 | 6 | 4 | 4 | 5 | 0 | 5 | 7 | 7 | 6 | 6 | 4 | 0 | 6 | 4 | 6 | 5 | 5 | 6 | 3 | 3 | 3 | 0 | 4 | 5 | 4 | 2 | 5 | 6 | 4 | 4 | 5 | 4 | 4 | 5 | 0 | 0 | 0 | 0