## Match-2026DLR -UPTO AUG -25
Dayakar DLR Report B&E
Sl.No | Date | Activity | Location/ Description | Qty. | Remarks
III. |  | 2025-03-01 | Average Manpower : | 7 | Nos
| 2025-03-01 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing
2 |  | Rope Pulling | 31st Floor | 2
3 |  | Toiet Open Conduit
4 |  | Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
Pending/ Snag Points :
10 |  | Rope Pulling | 31st Floor Chokeups | 2
11 |  | Wiring | Pending points | 3
12 |  | Gypsum board Clearance Works | 6th& 10th Floor | 4
|  | Total Manpower |  | 11
| 2025-03-02 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing
2 |  | Rope Pulling
3 |  | Toiet Open Conduit
4 |  | Wiring | 6th Floor Continuity | 2
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
Pending/ Snag Points :
10 |  | Rope Pulling
11 |  | Wiring
12 |  | Gypsum board Clearance Works | Dummys Fixing | 3
|  | Total Manpower |  | 5
| 2025-03-03 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Terrace | 2
2 |  | Rope Pulling | 31st Floor | 2
3 |  | Toiet Open Conduit
4 |  | Wiring | 10th Floor Continuity | 3 | 9th Floor Continuity still pending
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
Pending/ Snag Points :
10 |  | Rope Pulling
11 |  | Wiring
12 |  | Gypsum board Clearance Works | 10th Floor Dummy/ Flexibles | 2
|  | Total Manpower |  | 9
| 2025-03-04 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Terrace | 2
2 |  | Rope Pulling | 31st Floor | 2
3 |  | Toiet Open Conduit
4 |  | Wiring |  | 3
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M |  | 2
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
Pending/ Snag Points :
10 |  | Rope Pulling
11 |  | Wiring
12 |  | Gypsum board Clearance Works | 11th Floor Dummy/ Flexibles | 2
|  | Total Manpower |  | 11
| 2025-03-05 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Terrace | 2
2 |  | Rope Pulling | 31st Floor | 2
3 |  | Toiet Open Conduit
4 |  | Wiring | 903 Continuity | 2
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
Pending/ Snag Points :
10 |  | Rope Pulling
11 |  | Wiring | Pending points& Gasmeter Cabling | 3
12 |  | Gypsum board Clearance Works
|  | Total Manpower |  | 9
| 2025-03-06 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Terrace | 2
2 |  | Rope Pulling | 31st Floor | 2
3 |  | Toiet Open Conduit
4 |  | Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M |  | 2
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
Pending/ Snag Points :
10 |  | Rope Pulling
11 |  | Wiring
12 |  | Gypsum board Clearance Works
13 |  | Foot lamp rectification works | 8th floor | 2
|  | Total Manpower |  | 8
| 2025-03-07 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing
2 |  | Rope Pulling
3 |  | Toiet Open Conduit
4 |  | Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
Pending/ Snag Points :
10 |  | Rope Pulling
11 |  | Wiring | 6th Floor | 2
12 |  | Gypsum board Clearance Works
13 |  | Foot lamp rectification works
6 |  | Ledge Wall 4M | Rectification works | 2
|  | Total Manpower |  | 4
| 2025-03-08 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Terrace conduiting | 2
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
Pending/ Snag Points :
10 |  | Rope Pulling
11 |  | Wiring | 9th floor snag points | 2
12 |  | Ledge Wall 4M | Measurement Rectification
13 |  | Gypsum board Clearance Works | 5th&6th floor snag points | 2
14 |  | Foot lamp rectification works | 8th floor | 2
|  | Total Manpower |  | 8
| 2025-03-09 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Terrace conduiting | 3
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
Pending/ Snag Points :
10 |  | Rope Pulling
11 |  | Wiring
12 |  | Gypsum board Clearance Works
13 |  | Foot lamp rectification works | 8th floor | 2
|  | Total Manpower |  | 5
| 2025-03-10 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
Pending/ Snag Points :
10 |  | Rope Pulling
11 |  | Wiring
12 |  | Gypsum board Clearance Works | 6th,9th Floor Snag& 11th Dummy Fixing | 4
13 |  | Foot lamp rectification works | 8th Floor | 2
|  | Total Manpower |  | 6
| 2025-03-11 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing |  | 2 | STP
2 |  | Rope Pulling | 29th Checking | 2
3 |  | Toilet Open Conduit
4 |  | Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
Pending/ Snag Points :
10 |  | Rope Pulling
11 |  | Wiring | Sang points | 2
12 |  | Gypsum board Clearance Works | 11th floor AC Boxes
13 |  | Foot lamp rectification works | 8th Floor | 2
|  | Total Manpower |  | 8
| 2025-03-12 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing |  | 2 | STP
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
Pending/ Snag Points :
10 |  | Rope Pulling | 29th Floor | 2
11 |  | Wiring | Sang points | 2
12 |  | Gypsum board Clearance Works | 11th floor AC Boxes
13 |  | Foot lamp rectification works | 8th& 9th Floor | 2
|  | Total Manpower |  | 8
| 2025-03-13 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing |  | 2 | STP
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
Pending/ Snag Points :
10 |  | Rope Pulling | Staircases 2nd to below floors open conduit removal& making concealed, 29th post checking snag. | 3 |  | 1
11 |  | Wiring
12 |  | Gypsum board Clearance Works | 12th Floor Dummys | 1
13 |  | Foot lamp rectification works
|  | Total Manpower |  | 6
| 2025-03-14 | Running Works: |  |  | No manpower Due to Holi Festival
1 |  | Slab/ Wall Conduit& Box fixing
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
Pending/ Snag Points :
10 |  | Rope Pulling
11 |  | Wiring
12 |  | Gypsum board Clearance Works
13 |  | Foot lamp rectification works
|  | Total Manpower |  | 0
| 2025-03-15 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing
2 |  | Rope Pulling | 30th Floor Post Checking | 1
3 |  | Toilet Open Conduit
4 |  | Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling | Staircases Below Floors Open Conduit Removing& Route Clearance, | 2 |  | 1
12 |  | Wiring
13 |  | Gypsum board Clearance Works | 12th Floor Dummys& Flexibles | 1
14 |  | Foot lamp rectification works
15 |  | Ledge Wall 4M | Measurement Rectification | 2
|  | Total Manpower |  | 6
| 2025-03-16 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Tower -E 101 | 2
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling
12 |  | Wiring
13 |  | Gypsum board Clearance Works | 12th Floor Dummys& Flexibles | 1
14 |  | Foot lamp rectification works
15 |  | Ledge Wall 4M | Measurement Rectification | 1
|  | Total Manpower |  | 4
| 2025-03-17 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Tower -E 101 | 1
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling | Staircases Below Floors Open Conduit Removing& Route Clearance | 2 |  | 1
12 |  | Wiring
13 |  | Gypsum board Clearance Works | 14th Floor AC Box Fixing | 1
14 |  | Foot lamp rectification works
15 |  | Ledge Wall 4M | Measurement Rectification | 1
|  | Total Manpower |  | 5
| 2025-03-18 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Tower -E 101 | 2
2 |  | Rope Pulling | 30th Floor Checking | 2
3 |  | Toilet Open Conduit
4 |  | Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling | Staircases Below Floors Open Conduit Removing& Route Clearance | 2 |  | 1
12 |  | Wiring
13 |  | Gypsum board Clearance Works
14 |  | Foot lamp rectification works
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 6
| 2025-03-19 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Tower -E 101 | 2
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling | Staircases of Below Floors Open Conduit Removing& Route Clearance | 2 |  | 1
12 |  | Wiring
13 |  | Gypsum board Clearance Works
14 |  | Foot lamp rectification works
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 4
| 2025-03-20 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Tower -E 101 | 2
2 |  | Rope Pulling | 30th Floor Ope pulling Checking | 2
3 |  | Toilet Open Conduit
4 |  | Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling | Staircases of Below Floors Open Conduit Removing& Route Clearance | 2 |  | 1
12 |  | Wiring
13 |  | Gypsum board Clearance Works
14 |  | Foot lamp rectification works
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 6
| 2025-03-21 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Tower -E 101 | 3
2 |  | Rope Pulling | 30th Floor Rope pulling Checking | 2
3 |  | Toilet Open Conduit
4 |  | Wiring | 202 Mockup& 10th Floor Continuity Checking | 2
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling | General Staircase Route checking | 2
12 |  | Wiring
13 |  | Gypsum board Clearance Works
14 |  | Foot lamp rectification works
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 9
| 2025-03-22 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Tower -E 101 | 3
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Wiring | 202 Mockup& 10th Floor Continuity Checking | 2
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling | General Staircase 20th to 10th Floor Route Clearance | 2
12 |  | Wiring
13 |  | Gypsum board Clearance Works
14 |  | Foot lamp rectification works
15 |  | Ledge Wall 4M | 21st Floor to 24th Floor Measurement Rectification | 2
|  | Total Manpower |  | 9
| 2025-03-23 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Tower -E 101 | 3
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying | 24th Floor | 1
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling | General Staircase Route Clearance checking 10th Floor to 1st Floor | 2
12 |  | Wiring | 9th Floor | 2
13 |  | Gypsum board Clearance Works
14 |  | Foot lamp rectification works
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 8
| 2025-03-24 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Tower -E 101 | 3
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Wiring | 10th Floor Continuity test | 2
5 |  | AEDB Fixing | 24th& 25th Floor | 1
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling | Genral Staircase Conduit Route Clearance | 2
12 |  | Wiring | 9th Floor wiring snag , 30th Floor post checking& snag points. | 2
13 |  | Gypsum board Clearance Works
14 |  | Foot lamp rectification works
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 10
| 2025-03-25 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Tower -E 101 | 2
2 |  | Rope Pulling | 30th floor
3 |  | Toilet Open Conduit
4 |  | Wiring | 10th Floor Continuity test | 2
5 |  | AEDB Fixing | 24th& 25th Floor | 1
6 |  | Ledge Wall 4M | 25th& 26th Floor | 2
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling | Genral Staircase Conduit Route Clearance
12 |  | Wiring
13 |  | Gypsum board Clearance Works
14 |  | Foot lamp rectification works
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 7
| 2025-03-26 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Tower -E 101 | 2
2 |  | Rope Pulling | 30th floor
3 |  | Toilet Open Conduit
4 |  | Wiring | 10th Floor Continuity test | 2
5 |  | AEDB Fixing | 24th& 25th Floor
6 |  | Ledge Wall 4M | 25th& 26th Floor
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling | Genral Staircase Conduit Route Clearance | 1
12 |  | Wiring
13 |  | Gypsum board Clearance Works
14 |  | Foot lamp rectification works
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 5
| 2025-03-27 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Tower -E 101 | 1
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling
12 |  | Wiring
13 |  | Gypsum board Clearance Works
14 |  | Foot lamp rectification works
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 1
| 2025-03-28 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Tower -E 101 | 1
2 |  | Rope Pulling | 31st floor pending & checking | 1
3 |  | Toilet Open Conduit
4 |  | Wiring | 10th Floor Continuity test & QC points fixing | 2
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling | Staircase Conduit Route Clearance | 2
12 |  | Wiring
13 |  | Gypsum board Clearance Works
14 |  | Foot lamp rectification works | 8th floor | 2
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 8
| 2025-03-29 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Tower - E, B -3 Temporary Lighting. | 2
2 |  | Rope Pulling | 31st floor thread pulling pendings & checking | 1
3 |  | Toilet Open Conduit
4 |  | Wiring | 10th Floor Continuity test & QC points fixing | 3
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling | Staircase Conduit Route Clearance | 2
12 |  | Wiring
13 |  | Gypsum board Clearance Works
14 |  | Foot lamp rectification works | 8th floor | 2
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 10
| 2025-03-30 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Tower - E, B -3 Temporary Lighting. | 2
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M | 26th Floor | 1
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling
12 |  | Wiring
13 |  | Gypsum board Clearance Works | 12th& 13th Floor Flexibles Laying | 3
14 |  | Foot lamp rectification works | 9th Floor | 2
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 8
| 2025-03-31 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | E-Block | 2
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling | Fire Staircase Route Clearance | 2
12 |  | Wiring
13 |  | Gypsum board Clearance Works | 12th& 13th Floor Flexibles Laying | 2
14 |  | Foot lamp rectification works
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 6
IV. |  | 2025-04-01 | Average Manpower : | 13 | Nos
| 2025-04-01 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Tower -E | 1
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Wiring | ODU Cabling 303,803,903& 202 Lights temp conn. | 2
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling | Fire Staircase Route Clearance | 2
12 |  | Wiring
13 |  | Gypsum board Clearance Works
14 |  | Foot lamp rectification works | 9th Floor | 2
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 7
| 2025-04-02 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Tower -E | 0
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling | Staircase Route Clearance | 2
12 |  | Wiring
13 |  | Gypsum board Clearance Works | 12th& 13th Floor Flexibles& AC box fixing& RO conduiting | 3
14 |  | Foot lamp rectification works | 9th Floor | 2
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 7
| 2025-04-03 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Tower -E | 0
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling | Staircase Route Clearance | 2
12 |  | Wiring
13 |  | Gypsum board Clearance Works | 12th& 13th Floor Flexibles& AC box fixing& RO conduiting | 3
14 |  | Foot lamp rectification works | 9th Floor | 2
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 7
| 2025-04-04 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Tower -E | 0
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling
12 |  | Wiring | 9th Floor pendings & snag points | 2
13 |  | Gypsum board Clearance Works | 12th& 13th Floor Flexibles& AC box fixing& RO conduiting | 4
14 |  | Foot lamp rectification works | 10th Floor | 2
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 8
| 2025-04-05 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Tower -E | 0
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling | Fire Staircase Route Clearance | 1
12 |  | Wiring | 9th Floor pendings & snag points | 1
13 |  | Gypsum board Clearance Works | 12th& 13th Floor Flexibles& AC box fixing | 2
14 |  | Foot lamp rectification works | 10th Floor | 2
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 6
| 2025-04-06 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling | Fire Staircase Route Clearance | 2
12 |  | Wiring | 10th Floor Snag points | 2
13 |  | Gypsum board Clearance Works | 13th Floor AC Box Fixing& Drop Flexibles laying | 2
14 |  | Foot lamp rectification works | 10th Floor Footlamps | 2
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 8
| 2025-04-07 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Tower -E | 4
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Wiring | Preparing for Continuity checking | 2
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling
12 |  | Wiring | 9th& 10th Floor Wiring Snag points | 1
13 |  | Gypsum board Clearance Works | 13th Floor AC Box Fixing& Drop Flexibles laying | 2
14 |  | Foot lamp rectification works | 10th Floor Footlamps | 2
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 11
| 2025-04-08 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Tower -E | 4
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Wiring | Preparing for Continuity checking | 2
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling
12 |  | Wiring | 9th& 10th Floor Wiring Snag points | 1
13 |  | Gypsum board Clearance Works | 13th Floor AC Box Fixing& Drop Flexibles laying | 2
14 |  | Foot lamp rectification works | 10th Floor Footlamps | 2
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 11
| 2025-04-09 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Tower -E | 7
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Wiring | 11th floor continuity checking & pendings | 2
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling
12 |  | Wiring | Stair case wiring & 20th floor wiring pendings | 5
13 |  | Gypsum board Clearance Works
14 |  | Foot lamp rectification works | 10th Floor Footlamps | 2
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 16
| 2025-04-10 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Tower -E | 3
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring | 11th floor continuity checking & pendings | 2
|  | Staircase Wiring | General Staircase | 2
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling | 1st Floor to B3 Route checking | 2
12 |  | Wiring | 11th, 12th, 13th Floor Pending Points | 4
13 |  | Gypsum board Clearance Works
14 |  | Foot lamp rectification works | 11th Floor | 2
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 15
| 2025-04-11 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Tower -E (Conduiting Ckecking | 2
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring | 12th floor continuity checking -02& 21st Floor Wiring -04 | 6
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling | 1F to B1 General Staircase Route Clearance | 2
12 |  | Wiring | 11th& 12th Floor Snag points | 2
13 |  | Gypsum board Clearance Works
14 |  | Foot lamp rectification works | 11th Floor | 2
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 14
| 2025-04-12 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Tower -E (Conduiting Ckecking | 2
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring | 21st floor wiring | 4
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling | Staircase rooting checking | 2
12 |  | Wiring | 12th floor continuity checking -02& 21st Floor Wiring -04 | 4
13 |  | Gypsum board Clearance Works
14 |  | Foot lamp rectification works | 11th floor foot lamp rectification work | 2
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 14
| 2025-04-13 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Tower -E (Conduiting Ckecking) | 2
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring | 22nd floor wiring | 4
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling | Stair case route checking | 2
12 |  | Wiring | 11th & 12th wiring snag points | 4
13 |  | Gypsum board Clearance Works | 13th floor flexible fixing | 2
14 |  | Foot lamp rectification works
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 14
| 2025-04-14 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Tower -E (Conduiting Ckecking | 2
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring | 22nd floor wiring | 4
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling | Staircase rooting checking | 3
12 |  | Wiring | 13th floor continuity checking & 11th, 12th wiring snag points | 4
13 |  | Gypsum board Clearance Works
14 |  | Foot lamp rectification works
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 13
| 2025-04-15 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Tower -E | 2
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring | 22nd floor wiring | 2
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling | Staircase rooting checking | 3
12 |  | Wiring | 13th floor continuity checking & 11th, 12th wiring snag points | 4
13 |  | Gypsum board Clearance Works
14 |  | Foot lamp rectification works
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 11
| 2025-04-16 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Tower -E | 2
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring | 22nd floor wiring | 2
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling | Staircase rooting checking | 2
12 |  | Wiring | 20th pending points & RSP earth studs manpower | 4
13 |  | Gypsum board Clearance Works
14 |  | Foot lamp rectification works
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 10
| 2025-04-17 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring | 22nd floor wiring | 2
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling
12 |  | Wiring | 20th pending points & staircase rooting checking | 4
13 |  | Gypsum board Clearance Works | 14th & 13th floor flexible fixing & AC box fixing | 4
14 |  | Foot lamp rectification works
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 10
| 2025-04-18 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Tower-E 101 Screw Open work & 102 wall conduiting work | 2
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring | 21st floor wiring | 4
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling
12 |  | Wiring | 20th floor wiring pendings | 2
13 |  | Gypsum board Clearance Works | 12th floor snag points & 13th floor flexible fixing & AC box fixing | 4
14 |  | Foot lamp rectification works | 1st floor foot lamp rectification work | 2
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 14
| 2025-04-19 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring | 21st floor wiring | 4
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling
12 |  | Wiring | 20th floor wiring pendings & staircase wiring | 4
13 |  | Gypsum board Clearance Works | 13th floor flexible fixing & AC box fixing, corecutting pending & 14th floor pendings | 4
14 |  | Foot lamp rectification works | 10th & 11th floor foot lamp rectification works | 2
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 14
| 2025-04-20 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring | 23rd floor wiring | 2
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling
12 |  | Wiring
13 |  | Gypsum board Clearance Works | 13th & 14th floor flexible fixing & AC box fixing, corecutting pending & 14th floor pendings | 7
14 |  | Foot lamp rectification works | 1st floor hooter rectification work | 2
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 11
| 2025-04-21 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring | 22nd & 23rd floor wiring | 4
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling
12 |  | Wiring
13 |  | Gypsum board Clearance Works | 13th & 14th floor flexible fixing & AC box fixing, corecutting pending & 14th floor pendings | 5
14 |  | Foot lamp rectification works | 11th floor foot lamp rectification works | 2
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 11
| 2025-04-22 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Tower-E 102 Wall conduiting work | 2
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring | 23rd floor wiring | 2
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting | Temporary Lighting | 1
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling
12 |  | Wiring | Staircase wiring | 2
13 |  | Gypsum board Clearance Works | 13th & 14th floor flexible fixing & AC box fixing, corecutting pending & 14th floor pendings | 7
14 |  | Foot lamp rectification works | 11th floor foot lamp rectification works | 2
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 16
| 2025-04-23 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Tower-E 102 Wall conduiting work | 3
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring | 23rd floor wiring | 2
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting | Temporary Lighting | 1
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling
12 |  | Wiring | Staircase wiring & 1003, 1103 ODU cable laying | 4
13 |  | Gypsum board Clearance Works | 13th & 14th floor flexible fixing & AC box fixing, corecutting pending & 14th floor pendings | 5
14 |  | Foot lamp rectification works | 12th floor foot lamp rectification works | 2
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 17
| 2025-04-24 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring | 23rd floor wiring | 6
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling
12 |  | Wiring | Staircase Route checking & wiring | 2
13 |  | Gypsum board Clearance Works | 13th & 14th floor core-cutting rectification & pendings & 31st floor thread pulling | 5
14 |  | Foot lamp rectification works | 12th & 13th floor foot lamp rectification works | 2
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 15
| 2025-04-25 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | 102 wall conduiting work manpower | 2
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring | 23rd floor wiring | 4
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | Pending/ Snag Points :
11 |  | Rope Pulling | 32nd floor thread pulling | 2
12 |  | Wiring | Staircase Route checking & wiring | 2
13 |  | Gypsum board Clearance Works | 13th & 14th & 15th floor core-cutting rectification & pendings & | 5
14 |  | Foot lamp rectification works | 13th floor footlamp rectification work | 2
15 |  | Ledge Wall 4M
|  | Total Manpower |  | 17
| 2025-04-26 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | 102 wall conduiting work manpower | 3
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring | 23rd floor wiring | 4
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing | 27th & 28th floor DB fixing | 2
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling | 32nd floor thread pulling | 2
13 |  | Wiring | Staircase Route checking & wiring | 2
14 |  | Gypsum board Clearance Works | 13th & 14th & 15th floor core-cutting rectification & pendings & | 5
15 |  | Foot lamp rectification works | 13th floor footlamp rectification work | 2
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 20
| 2025-04-27 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | 102 wall conduiting work manpower | 2
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring | 23rd floor wiring 1601 refuse area wiring | 4
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing | 28th & 6th floor DB rectification work | 2
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling | 32nd floor thread pulling | 2
13 |  | Wiring | Staircase Route checking & wiring | 2
14 |  | Gypsum board Clearance Works | 12th, 14th, 15th floors snag points | 5
15 |  | Foot lamp rectification works | 13th floor footlamp rectification work | 2
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 19
| 2025-04-28 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | 102 wall conduiting work manpower | 5
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring | 23rd & 24th floor wiring | 2
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling
13 |  | Wiring | 20,21,22,23 gas cable laying | 2
14 |  | Gypsum board Clearance Works | 14,15 AC box fixing & flexibles1303 core-cutting rectification & 30th floor pending work | 7
15 |  | Foot lamp rectification works | 14th floor footlamp rectification work | 2
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 18
| 2025-04-29 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | 102 wall conduiting work manpower | 2
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring | 2401 floor wiring | 4
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling
13 |  | Wiring
14 |  | Gypsum board Clearance Works | 1303 core-cutting rectification & 30,32 floor pendings | 3
15 |  | Foot lamp rectification works | 14th floor footlamp rectification work | 2
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 11
| 2025-04-30 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 102 wall conduiting | 4
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring | 24th floor wiring | 4
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing | 28th floor | 1
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling | 32nd floor | 2
13 |  | Wiring
14 |  | Gypsum board Clearance Works | 13th & 14th floor pendings | 4
15 |  | Foot lamp rectification works | 14th floor footlamp rectification work | 2
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 17
V. |  | 2025-05-01 | Average Manpower : | 16 | Nos
| 2025-05-01 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling
13 |  | Wiring
14 |  | Gypsum board Clearance Works
15 |  | Foot lamp rectification works
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 0
| 2025-05-02 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 102 wall conduiting | 3
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring | 24th floor wiring | 6
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling | 32nd floor thread pulling & terrace conduiting | 3
13 |  | Wiring
14 |  | Gypsum board Clearance Works
15 |  | Foot lamp rectification works | 14th floor footlamp rectification work | 2
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 14
| 2025-05-03 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | Terrace slab monitoring | 1
2 |  | Rope Pulling | 32nd floor thread pulling | 2
3 |  | Toilet Open Conduit
4 |  | Internal Wiring | 24th & 25th floor wiring | 4
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling
13 |  | Wiring
14 |  | Gypsum board Clearance Works | 14th&13th&16th | 5
15 |  | Foot lamp rectification works | 14th floor footlamp rectification work | 2
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 14
| 2025-05-04 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 102 wall conduiting | 4
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring | 24th & 25th floor wiring | 6
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling | 32nd floor thread pulling | 2
13 |  | Wiring
14 |  | Gypsum board Clearance Works | 11th & 14th | 4
15 |  | Foot lamp rectification works | 15th floor foot lamp rectification | 2
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 18
| 2025-05-05 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 102 wall conduiting | 4
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring | 24th & 25th floor wiring | 4
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying | 1903&2002&2003 | 2
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling | 32nd floor thread pulling & 3103 post checking | 2
13 |  | Wiring
14 |  | Gypsum board Clearance Works
15 |  | Foot lamp rectification works | 15th floor foot lamp rectification | 2
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 14
| 2025-05-06 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 102, 201 wall conduiting | 4
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring | 25th floor wiring | 4
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling | 32nd floor thread pulling & 3103 post checking | 2
13 |  | Wiring
14 |  | Gypsum board Clearance Works | 2003 & 1603 Flexible & Fan Rod Rod fixing | 4
15 |  | Foot lamp rectification works | 15th floor foot lamp rectification | 2
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 16
| 2025-05-07 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 102, 201 wall conduiting | 4
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring | 25th floor wiring | 4
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling | 32nd floor thread pulling & 3103 post checking | 2
13 |  | Wiring
14 |  | Gypsum board Clearance Works | 14th floor continuity testing & 17th Fan Rod Rod fixing | 4
15 |  | Foot lamp rectification works | 15th floor foot lamp rectification | 2
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 16
| 2025-05-08 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 102, 201 wall conduiting | 10
2 |  | Rope Pulling
3 |  | Toilet Open Conduit | 32nd Floor | 2
4 |  | Internal Wiring | 25th floor wiring | 4
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling | 32nd floor thread pulling & 3103 post checking | 2
13 |  | Wiring
14 |  | Gypsum board Clearance Works | 21st & 14th floor continuity testing & 17th Fan Rod Rod fixing | 5
15 |  | Foot lamp rectification works | 15th floor foot lamp rectification | 2
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 25
| 2025-05-09 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 102, 201, 103 wall conduiting | 10
2 |  | Rope Pulling
3 |  | Toilet Open Conduit | 32nd Floor | 2
4 |  | Internal Wiring | 2501, 2503, 2603 floor wiring | 4
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling | 32nd floor thread pulling & 3103 post checking | 2
13 |  | Wiring
14 |  | Gypsum board Clearance Works | 21st & 14th floor continuity testing & 17th Fan Rod Rod fixing | 5
15 |  | Foot lamp rectification works | 15th floor foot lamp rectification | 2
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 25
| 2025-05-10 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 102, 201, 103 wall conduiting | 10
2 |  | Rope Pulling
3 |  | Toilet Open Conduit | 31st Floor | 2
4 |  | Internal Wiring | 25th floor wiring | 2
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling | 32nd floor thread pulling | 2
13 |  | Wiring
14 |  | Gypsum board Clearance Works | 1502 Testing, 16th floor flexible & dummy's | 3
15 |  | Foot lamp rectification works
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 19
| 2025-05-11 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 102, 201, 103 wall conduiting | 8
2 |  | Rope Pulling
3 |  | Toilet Open Conduit | 32nd Floor | 2
4 |  | Internal Wiring | 25th floor wiring | 2
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling
13 |  | Wiring
14 |  | Gypsum board Clearance Works | 15 & 16th floor flexible & dummy's & 22nd floor dummy's & AC Boxfixing | 6
15 |  | Foot lamp rectification works
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 18
| 2025-05-12 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 102, 201, 103 wall conduiting | 5
2 |  | Rope Pulling
3 |  | Toilet Open Conduit | 31st Floor | 2
4 |  | Internal Wiring | 27th floor wiring | 2
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling | 32nd floor thread pulling | 2
13 |  | Wiring
14 |  | Gypsum board Clearance Works | 17 & 18th floor flexible & dummy's & AC Boxfixing | 2
15 |  | Foot lamp rectification works
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 13
| 2025-05-13 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 201, 102, 103 wall conduiting | 6
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring | 27th wiring & 24th floor KNX cable | 4
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying | 23rd floor | 2
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling
13 |  | Wiring
14 |  | Gypsum board Clearance Works | 23rd floor flexible & dummy's | 1
15 |  | Foot lamp rectification works
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 13
| 2025-05-14 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 201, 103 wall conduiting | 4
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring | 27th floor wiring & 24th floor KNX cable | 4
|  | Staircase Wiring | Staircase Route checking | 2
5 |  | AEDB Fixing | 29th floor | 2
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling
13 |  | Wiring
14 |  | Gypsum board Clearance Works | 23rd floor flexible & dummy's | 1
15 |  | Foot lamp rectification works
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 13
| 2025-05-15 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 201, 102, 103 wall conduiting | 6
2 |  | Rope Pulling | 32nd floor | 2
3 |  | Toilet Open Conduit
4 |  | Internal Wiring | 25th floor KNX wiring | 2
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling
13 |  | Wiring | 15th floor continuity & 14th snag points | 4
14 |  | Gypsum board Clearance Works | 16th floor flexible & dummy's | 1
15 |  | Foot lamp rectification works
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 15
| 2025-05-16 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 201, 102, 103 wall conduiting | 7
2 |  | Rope Pulling | 32nd floor | 2
3 |  | Toilet Open Conduit
4 |  | Internal Wiring | 25th Floor | 2
|  | Staircase Wiring | Stair case | 2
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M | 25th Ledge wall and Terrace Wall | 2
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling | FA Points | 2
13 |  | Wiring
14 |  | Gypsum board Clearance Works | 22nd floor flexible & fan rod fixing | 2
15 |  | Foot lamp rectification works
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 19
| 2025-05-17 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 102, 103 wall conduiting | 4
2 |  | Rope Pulling | 32nd floor | 2
3 |  | Toilet Open Conduit
4 |  | Internal Wiring | 26th & 25th Floor | 2
|  | Staircase Wiring | Stair case | 2
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M | 25th Ledge wall and Terrace Wall | 2
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling | FA Points | 2
13 |  | Wiring
14 |  | Gypsum board Clearance Works | 24th floor flexible & fan rod fixing | 2
15 |  | Foot lamp rectification works
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 16
| 2025-05-18 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 102, 103 wall conduiting | 5
2 |  | Rope Pulling | 32nd floor | 2
3 |  | Toilet Open Conduit
4 |  | Internal Wiring | 26th Floor | 2
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing | DB wire's packing | 2
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling
13 |  | Wiring
14 |  | Gypsum board Clearance Works | 24th & 18th floor flexible & fan rod fixing | 5
15 |  | Foot lamp rectification works
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 16
| 2025-05-19 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 102, 103 wall conduiting | 4
2 |  | Rope Pulling
3 |  | Toilet Open Conduit | 32nd floor | 2
4 |  | Internal Wiring | 26th Floor | 3
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing | DB wire's packing | 1
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling
13 |  | Wiring | 15th snags | 2
14 |  | Gypsum board Clearance Works | 24th & 18th floor AC box, flexible & fan rod fixing | 5
15 |  | Foot lamp rectification works
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 17
| 2025-05-20 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 102, 103 wall conduiting | 5
2 |  | Rope Pulling
3 |  | Toilet Open Conduit | 32nd floor | 2
4 |  | Internal Wiring | 26th Floor | 2
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing | 30th DB fixing | 2
|  | Basements | STB Room Thread Pulling | 2
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling
13 |  | Wiring | 16th snags | 2
14 |  | Gypsum board Clearance Works
15 |  | Foot lamp rectification works
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 15
| 2025-05-21 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 103, 201 wall conduiting | 7
2 |  | Rope Pulling
3 |  | Toilet Open Conduit | 32nd floor | 2
4 |  | Internal Wiring | 26th Floor | 2
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
|  | Basements | STB Room Thread Pulling | 2
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling
13 |  | Wiring | 13th, 14th & 16th snags | 4
14 |  | Gypsum board Clearance Works | 25th floor | 2
15 |  | Foot lamp rectification works
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 19
| 2025-05-22 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 201, 103 wall conduiting | 7
2 |  | Rope Pulling | Staircase | 2
3 |  | Toilet Open Conduit
4 |  | Internal Wiring | 28th Floor | 2
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
|  | Basements | STB Room Thread Pulling | 2
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling
13 |  | Wiring | 15th snags | 2
14 |  | Gypsum board Clearance Works | 17th floor AC Box fixing | 1
15 |  | Foot lamp rectification works | 16th floor | 2
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 18
| 2025-05-23 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 201, 103 wall conduiting | 7
2 |  | Rope Pulling | Staircase | 2
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
|  | Basements | STB Room Thread Pulling | 2
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling
13 |  | Wiring | 15th snags | 2
14 |  | Gypsum board Clearance Works | 1601 testing checking | 2
15 |  | Foot lamp rectification works | 16th floor | 2
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 17
| 2025-05-24 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 103, 102 wall conduiting, 201 slab conduiting | 6
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
|  | Basements | Basements STB Room Thread Pulling | 2
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling
13 |  | Wiring | 15th & 16th snags | 4
14 |  | Gypsum board Clearance Works | 1601 testing checking | 2
15 |  | Foot lamp rectification works | 16th floor | 2
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 16
| 2025-05-25 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 103, 102 wall conduiting, 201 slab conduiting | 7
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling
13 |  | Wiring | 14th,15th,16th snags | 6
14 |  | Gypsum board Clearance Works
15 |  | Foot lamp rectification works | 16th floor & footlamp fixing | 3
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 16
| 2025-05-26 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 103, 102 wall conduiting, 201 slab conduiting | 7
2 |  | Rope Pulling | Terrace | 1
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling
13 |  | Wiring | 15th,16th snags | 6
14 |  | Gypsum board Clearance Works
15 |  | Foot lamp rectification works
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 14
| 2025-05-27 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 103, 102 wall conduiting, 201 slab conduiting | 7
2 |  | Rope Pulling | 32nd floor checking | 2
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling
13 |  | Wiring | 15th,16th snags | 4
14 |  | Gypsum board Clearance Works | 17th floor AC Box fixing | 1
15 |  | Foot lamp rectification works
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 14
| 2025-05-28 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 103, 102 wall conduiting, B-3 slab conduiting | 7
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
|  | Staircase Wiring | Staircase wiring | 2
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling
13 |  | Wiring | 17th Pending Works | 4
14 |  | Gypsum board Clearance Works
15 |  | Foot lamp rectification works
16 |  | Ledge Wall 4M | 15th, 14th, 13th | 2
|  | Total Manpower |  | 15
| 2025-05-29 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 103, 102 wall conduiting, B-3 slab conduiting | 8
2 |  | Rope Pulling | 32nd Floor | 2
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing | 10th Floor DB Packing | 1
Basements
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling
13 |  | Wiring | 17th Pending Works | 2
14 |  | Gypsum board Clearance Works | 26th Flecible Fixing | 1
15 |  | Foot lamp rectification works | 2nd Floor | 2
16 |  | Ledge Wall 4M | 15th, 14th, 13th | 2
|  | Total Manpower |  | 18
| 2025-05-30 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 103 wall conduiting, 101 drops & JB opening | 8
2 |  | Rope Pulling | 32nd Floor | 2
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling
13 |  | Wiring | 1701 checking | 2
14 |  | Gypsum board Clearance Works | 26th Flexible Fixing | 1
15 |  | Foot lamp rectification works | 18th floor | 2
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 15
| 2025-05-31 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 103 wall conduiting, 101 drops & JB opening | 8
2 |  | Rope Pulling | 32nd Floor | 2
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling
13 |  | Wiring | 1703 checking & 1701 snags | 4
14 |  | Gypsum board Clearance Works | 26th Flexible Fixing | 1
15 |  | Foot lamp rectification works | 2nd & 3rd floor | 2
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 17
VI. |  | 2025-06-01 | Average Manpower : | 12.1667 | Nos
| 2025-06-01 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 103 wall conduiting, 201 Screw Opening & staircase Conduiting | 7
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling
13 |  | Wiring | 17th checking | 2
14 |  | Gypsum board Clearance Works | 19th Roundsheets & flexible & AC Box | 2
15 |  | Foot lamp rectification works | 3rd & 4th floor | 2
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 13
| 2025-06-02 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 103 conduiting | 6
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling
13 |  | Wiring | 17 & 18 checkings & 19th pendings | 4
14 |  | Gypsum board Clearance Works | 19th Roundsheets & flexible & AC Box | 2
15 |  | Foot lamp rectification works | 3rd & 18th floor | 1
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 13
| 2025-06-03 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 103 conduiting & T-E B-3 Slab conduiting | 7
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling
13 |  | Wiring | 17 & 18 & 19 Floors snag points | 6
14 |  | Gypsum board Clearance Works | 19th Floor | 4
15 |  | Foot lamp rectification works | 4th & 18th | 2
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 19
| 2025-06-04 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 103 conduiting & T-E B-3 Slab conduiting | 7
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling
13 |  | Wiring | 18th checking | 4
14 |  | Gypsum board Clearance Works | 19th & 20 AC Box fixing | 2
15 |  | Foot lamp rectification works | 4th & 18th | 2
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 15
| 2025-06-05 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 103 conduiting & T-E B-3 Slab conduiting | 7
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling
13 |  | Wiring | 18th checking | 2
14 |  | Gypsum board Clearance Works | 19th & 20 AC Box fixing | 4
15 |  | Foot lamp rectification works | 4th & 18th | 2
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 15
| 2025-06-06 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 103 conduiting & B-3 Slab conduiting | 0
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling
13 |  | Wiring | 18th checking | 2
14 |  | Gypsum board Clearance Works | 19th & 20 AC Box fixing | 5
15 |  | Foot lamp rectification works | 4th & 18th | 2
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 9
| 2025-06-07 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 103 conduiting & T-E B-3 Slab conduiting | 0
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling
13 |  | Wiring
14 |  | Gypsum board Clearance Works | 20th fan rod & flexible AC box fixing | 3
15 |  | Foot lamp rectification works | 6th & 18th | 1
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 4
| 2025-06-08 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 103 Slab conduiting | 5
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling
13 |  | Wiring
14 |  | Gypsum board Clearance Works | 20th fan rod & flexible AC box fixing & 2nd Floor toilet pendings | 5
15 |  | Foot lamp rectification works | 18th snags | 2
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 12
| 2025-06-09 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 103 Slab conduiting | 4
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Rope Pulling
13 |  | Wiring
14 |  | Gypsum board Clearance Works | 20th fan rod & flexible AC box fixing & 2nd Floor toilet pendings | 6
15 |  | Foot lamp rectification works | 18th & 19th | 2
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 12
| 2025-06-10 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 103 Slab conduiting | 4
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Continuity Checking | 19th floor | 2
13 |  | Wiring | 26th Floor | 2
14 |  | Gypsum board Clearance Works | 17th floor snags | 2
15 |  | Foot lamp rectification works
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 10
| 2025-06-11 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 103 Slab conduiting | 2
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Continuity Checking
13 |  | Wiring | 26th Floor | 2
14 |  | Gypsum board Clearance Works | 17th & 18th floor snags | 4
15 |  | Foot lamp rectification works
16 |  | Ledge Wall 4M
|  | Total Manpower |  | 8
| 2025-06-12 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 103 Slab conduiting | 3
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Continuity Checking | 1802 | 2
13 |  | Wiring | 26th Floor | 2
14 |  | Gypsum board Clearance Works
15 |  | Foot lamp rectification works
16 |  |  | Lift shaft & Staircase | 4
|  | Total Manpower |  | 11
| 2025-06-13 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 103 Slab conduiting | 3
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Continuity Checking | 1802 | 2
13 |  | Wiring | 26th Floor | 2
14 |  | Gypsum board Clearance Works
15 |  | Foot lamp rectification works
16 |  |  | Lift shaft | 3
|  | Total Manpower |  | 10
| 2025-06-14 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 103 Slab conduiting | 4
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Continuity Checking | 1802 | 2
13 |  | Wiring | 27th Floor | 2
14 |  | Gypsum board Clearance Works
15 |  | Foot lamp rectification works
16 |  |  | Lift shaft | 3
|  | Total Manpower |  | 11
| 2025-06-15 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 103 Slab conduiting & 301 Box fixing | 6
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Continuity Checking
13 |  | Wiring
14 |  | Gypsum board Clearance Works
15 |  | Foot lamp rectification works
16
|  | Total Manpower |  | 6
| 2025-06-16 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E Slab Monitoring | 1
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
|  | Staircase Wiring | Staircase Wiring | 1
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Continuity Checking | 1802 | 2
13 |  | Wiring | 27th Floor | 2
14 |  | Gypsum board Clearance Works
15 |  | Foot lamp rectification works
16 |  |  | Terrace Conduiting, B1 Thread pulling | 6
|  | Total Manpower |  | 12
| 2025-06-17 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 103 screw opening & box paint marking & 202 box fixing wall conduiting | 5
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Continuity Checking
13 |  | Wiring | 28th Floor | 4
14 |  | Gypsum board Clearance Works
15 |  | Foot lamp rectification works
16 |  |  | Terrace Conduiting & B1 Thread pulling | 4
|  | Total Manpower |  | 13
| 2025-06-18 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 103 screw opening & box paint marking & 202 box fixing wall conduiting | 4
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Continuity Checking
13 |  | Wiring | 28th Floor | 4
14 |  | Gypsum board Clearance Works
15 |  | Foot lamp rectification works
16 |  |  | Terrace Conduiting & B1 Thread pulling | 6
|  | Total Manpower |  | 14
| 2025-06-19 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 202 box fixing wall conduiting | 4
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Continuity Checking | 18th snag | 2
13 |  | Wiring | 28th Floor | 4
14 |  | Gypsum board Clearance Works
15 |  | Foot lamp rectification works | 7th floor | 2
16 |  |  | B1 Thread pulling | 2
|  | Total Manpower |  | 14
| 2025-06-20 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 202 box fixing wall conduiting | 4
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Continuity Checking | 18th & 19th snag | 6
13 |  | Wiring | 29th & 30th Floor | 4
14 |  | Gypsum board Clearance Works
15 |  | Foot lamp rectification works
16 |  |  | B1 Thread pulling & Lift shaft wiring | 4
|  | Total Manpower |  | 18
| 2025-06-21 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 202 box fixing wall conduiting | 4
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Continuity Checking | 18th & 19th snag | 4
13 |  | Wiring | 30th Floor | 3
14 |  | Gypsum board Clearance Works
15 |  | Foot lamp rectification works | 8th floor | 2
16 |  |  | Lift shaft | 2
|  | Total Manpower |  | 15
| 2025-06-22 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 202 box fixing wall conduiting | 3
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Continuity Checking | 18th & 19th snag | 4
13 |  | Wiring
14 |  | Gypsum board Clearance Works
15 |  | Foot lamp rectification works
16 |  |  | Lift shaft | 6
|  | Total Manpower |  | 13
| 2025-06-23 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 202 box fixing wall conduiting | 3
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Continuity Checking | 18th & 19th snag | 4
13 |  | Wiring | 29th wiring | 2
14 |  | Gypsum board Clearance Works
15 |  | Foot lamp rectification works
16 |  | 3rd floor toilets | Lift shaft | 8
|  | Total Manpower |  | 17
| 2025-06-24 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 202 box fixing wall conduiting | 3
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Continuity Checking | 18th snag points | 2
13 |  | Wiring | 30th Floor | 2
14 |  | Gypsum board Clearance Works
15 |  | Foot lamp rectification works
16 |  |  | Lift shaft | 4
|  | Total Manpower |  | 11
| 2025-06-25 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 202 box fixing wall conduiting | 3
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Continuity Checking | 19th snag points | 2
13 |  | Wiring | 30th Floor | 2
14 |  | Gypsum board Clearance Works
15 |  | Foot lamp rectification works
16 |  | Other works | Lift shaft | 6
|  | Total Manpower |  | 13
| 2025-06-26 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 202 corridor pendings & 203 wall box fixings | 3
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Continuity Checking | 19th snag points | 1
13 |  | Wiring | 30th Floor | 2
14 |  | Gypsum board Clearance Works
15 |  | Foot lamp rectification works | 8th floor | 1
16 |  | Other works | Lift shaft | 4
|  |  | 27th Floor flexible & Round sheets & Fan rods | 2
|  | Total Manpower |  | 13
| 2025-06-27 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 203 wall box fixings | 3
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Continuity Checking | 20th & 1902 snag points | 4
13 |  | Wiring | 26th Floor KNX | 2
14 |  | Gypsum board Clearance Works
15 |  | Foot lamp rectification works
16 |  | Other works | Staircase | 1
|  | Total Manpower |  | 10
| 2025-06-28 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 203 wall box fixings | 4
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Continuity Checking | 2003 checking | 2
13 |  | Wiring | 1902 snag points | 2
14 |  | Gypsum board Clearance Works
15 |  | Foot lamp rectification works
16 |  | Other works | 16, 17, 18 floors MAED & AEDB packing | 1
|  | Total Manpower |  | 9
| 2025-06-29 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 203 wall box fixings, B2 slab Monitoring & 202 slab monitoring | 6
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Continuity Checking | 2003 snag points | 2
13 |  | Wiring | 1902 snag points | 2
14 |  | Gypsum board Clearance Works | 26th knx & 26th flexible | 2
15 |  | Foot lamp rectification works
16 |  | Other works | 3rd floor toilet clearance | 2
|  | Total Manpower |  | 14
| 2025-06-30 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 203 wall box fixings & B2 slab Monitoring | 4
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Continuity Checking | 2003 snag points | 2
13 |  | Wiring | 1902 snag points | 2
14 |  | Gypsum board Clearance Works | 27th flexible fixing | 2
15 |  | Foot lamp rectification works
16 |  | Other works | 3rd floor toilet clearance | 1
|  | Total Manpower |  | 11
VII |  | 2025-07-01 | Average Manpower : | 14.8571 | Nos
| 2025-07-01 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 203 wall & slab conduiting | 6
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Continuity Checking | 2103 snag points | 2
13 |  | Wiring | 1902 snag points | 2
14 |  | Gypsum board Clearance Works | 27th flexible fixing | 2
15 |  | Foot lamp rectification works
16 |  | Other works | 2nd floor AC sockets, AEDB checking, Ledge wall 4M, Fire staircase | 4
|  | Total Manpower |  | 16
| 2025-07-02 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 203 wall & slab conduiting | 6
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Continuity Checking | 21st & 22nd floors | 2
13 |  | Wiring
14 |  | Snag points | 2001 | 2
15 |  | Foot lamp rectification works
16 |  | Gypsum board Clearance Works
17 |  | Other works | 2nd floor AC sockets, AEDB checking, Ledge wall 4M, Fire staircase | 4
18 |  | Toilets Clearance
|  | Total Manpower |  | 14
| 2025-07-03 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 301 & 302 wall conduiting & 203 slab checking | 7
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Continuity Checking | 22nd floor | 2
13 |  | Wiring
14 |  | Snag points | 2001 | 2
15 |  | Foot lamp rectification works
16 |  | Gypsum board Clearance Works | 28th Flexible fixing | 2
17 |  | Toilets Clearance |  | 1
18 |  | Other works | Fire staircase | 1
|  | Total Manpower |  | 15
| 2025-07-04 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 301 & 302 wall conduiting & 203 slab checking | 7
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Flexible's & AC box fixing | 25th floor | 2
13 |  | Continuity Checking | 22nd floor | 2
14 |  | Snag points | 2001 | 2
15 |  | Foot lamp rectification works
16 |  | Gypsum board Clearance Works
17 |  | Toilets Clearance
18 |  | Other works | Fire staircase | 1
|  |  | 2nd Floor Mockup | 4
|  | Total Manpower |  | 18
| 2025-07-05 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 301 & 302 wall conduiting & 203 slab checking | 6
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Flexible's & AC box fixing | 26th floor | 2
13 |  | Continuity Checking | 22nd floor | 2
14 |  | Snag points | 2001 | 2
15 |  | Foot lamp rectification works
16 |  | Gypsum board Clearance Works
17 |  | Toilets Clearance
18 |  | Other works | 2nd floor light fixing, Toilet work, Ledge wall 29 & 30 floors | 8
|  | Total Manpower |  | 20
| 2025-07-06 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 302 slab conduiting | 6
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Flexible's & AC box fixing
13 |  | Continuity Checking
14 |  | Snag points
15 |  | Foot lamp rectification works
16 |  | Gypsum board Clearance Works
17 |  | Toilets Clearance
18 |  | Other works
|  | Total Manpower |  | 6
| 2025-07-07 | Running Works:
1 |  | Slab/ Wall Conduit& Box fixing | T-E 301 slab conduiting | 7
2 |  | Rope Pulling
3 |  | Toilet Open Conduit
4 |  | Internal Wiring
Staircase Wiring
5 |  | AEDB Fixing
6 |  | Ledge Wall 4M
7 |  | RO Pipe Laying
8 |  | LP Marking
9 |  | Temperary Lighting
10 |  | DB Fixing
Basements
11 |  | Pending/ Snag Points :
12 |  | Flexible's & AC box fixing | 27th floor | 4
13 |  | Continuity Checking
14 |  | Snag points | 21st & 22nd floors | 4
15 |  | Foot lamp rectification works
16 |  | Gypsum board Clearance Works
17 |  | Toilets Clearance
18 |  | Other works
|  | Total Manpower |  | 15

## Match-2026DLR-1 (hidden)
DLR& DPR Details
Contractor : Dayakar Electricals
Date | Tower -B |  |  |  |  | Tower -E
| Planned Works |  | Manpower (No's) | Work Status By EOD/ DPR | Remarks | PLANNED | Manpower (No's) | Status | Remarks
20-11-2025 | 1 | 2203 checking | 2
| 2 | 2nd floor mockup | 2
| 3 | 12&13 floor DB | 2
| 4 | staircase | 2
Total
| 1 | 29 floor communication | 2
| 2 | 21th floor toilet | 2
| 3 | staire case wiring | 1
| 4 | 12th floor toilet wiring | 2
Total
| 1 | 23 floor toilet wiring | 2
| 2 | 30th floor communication | 2
| 3 | 202 Switch board fixing | 3
| 4 | 1st floor foot lamp work | 2
Man power
| 1 | 30th floor communication | 2
| 2 | 202 Switch board fixing | 3
| 3 | 1st floor foot lamp work | 2
Man power
| 1 | 2203 Checking | 2
| 2 | 13th floor flat | 4
| 3 | 2nd floor foot lamp work | 2
Man power
| 1 | 16th floor toilet | 2
| 2 | 2nd floor foot lamp work | 2
Man power
| 1 | 12th & 13th floor DB | 1
| 2 | 2nd floor | 1
Man power
| 1 | 22 floor communication | 1
| 2 | 14th floor DB | 1
| 3 | lift shaft work | 3
| 4 | 19th floor foot lamp | 2
Man power
| 1 | 2203 Continuity Checking | 2
| 2 | lift shaft work | 4
| 3 | 19th floor foot lamp | 2
Man power
| 1 | 3002 flexible fixing | 1
| 2 | lift shaft work | 2
| 3 | 20th floor foot lamp | 2
Man power
| 1 | 3002 flexible fixing | 1
| 2 | lift shaft work | 3
Man power
| 1 | lift shaft work | 3
| 2 | 17th floor toilet | 2
| 3 | 3001 Ac Box fixing | 2
| 4 | 17th Fa Points | 2
|  | Man power | 9
| 1 | lift shaft work | 3
| 2 | B1 Slab Conduiting | 2
| 3 | 12th&13th Floor DB | 1
|  | Man power | 6
| 1 | lift shaft work | 3
| 2 | Club House | 2
|  | Man power | 5
| 1 | lift shaft work | 3
| 2 | B1 Slab Conduiting | 2
| 3 | 3rd Floor Corridor | 2
|  | Man power | 7
| 1 | 12th floor DB packing | 2
| 2 | B1 Slab Conduiting | 2
| 3 | 3rd Floor Corridor | 2
|  | Man power | 6
| 1 | 13 Floor DB packing | 2
|  | Man power | 2
| 1 | 11 th floor toilet | 2
| 2 | 16th floor toilet | 2
| 3 | 31st floor DB Fixing | 2
| 4 | 3rd floor celling lp marking | 2
|  | Man power | 8
| 1 | 3rd floor corridor | 2
| 2 | B1 Slab Conduiting | 2
| 3 | 31st floor DB Fixing | 2
| 4 | 2303 checking | 2
|  | Man power | 8
| 1 | 3rd floor corridor | 2
| 2 | 3rd floor Board cleaning | 2
| 3 | 2nd floor QC points | 2
| 4 | 16th DB packing | 2
|  | Man power | 8
| 1 | 3rd floor corridor | 2
| 2 | 3rd floor Board cleaning | 2
| 3 | 31st floor Knx Wiring | 2
| 4 | 16th and 15th toilet Work | 2
|  | Man power | 8
| 1 | 3rd floor corridor | 3
| 2 | 5th floor corridor wiring | 3
| 3 | 31st floor communication | 2
| 4 | 15th toilet Work | 1
|  | Man power | 9
| 1 | 3rd floor corridor | 4
| 2 | 5th floor corridor wiring | 3
| 3 | 17th18 toilet Work | 2
|  | Man power | 9
| 1 | 17thtoilet Work | 2
|  | Man power | 2
| 1 | 4rd floor corridor | 2
| 2 | 6th floor corridor wiring | 2
|  | Man power | 4
| 1 | 4rd floor corridor | 2
| 2 | 7th floor corridor wiring | 2
| 3 | 2303 Checking | 2
|  | Man power | 6
| 1 | 6rd floor corridor | 2
| 2 | 7th floor corridor wiring | 2
| 3 | 2302 Checking | 2
|  | Man power | 6
| 1 | 8rd floor corridor | 2
| 2 | 7th floor corridor wiring | 2
| 3 | 2302 Checking | 2
|  | Man power | 6
| 1 | 3102 wiring | 2
|  | Man power | 2
| 1 | 3201 wiring | 2
|  | Man power | 2
| 1 | 18th floor DB Packing | 1
| 2 | 22nd floor DB | 1
| 3 | 4th floor LP marking | 2
| 4 | 18th toilet Work | 2
|  | Man power | 6
| 1 | 22nd floor snag | 2
| 2 | 4th floor LP marking | 2
| 3 | 24th floor toilte work | 2
| 4 | 201 QC snag points | 1
| 5 | 22nd floor cutting chepping | 2
|  | Man power | 9
| 1 | 26th Floor toilte work | 2
| 2 | 2nd floor corridor conduting | 2
| 3 | passanger lift2 open conduting | 2
| 4 | 22nd floor cutting chepping | 2
|  | Man power | 8
| 1 | 18th Floor toilte work | 2
| 2 | 2nd floor corridor conduting | 2
| 3 | passanger lift2 open conduting | 2
| 4 | 2302&201 checking | 2
|  | Man power | 8
| 1 | 2nd floor corridor conduting | 2
| 2 | 3103 wiring | 2
| 3 | 401 LP marking | 2
| 4 | 27th toilet Work | 2
|  | Man power | 8
| 1 | 2nd floor corridor conduting | 2
| 2 | 23,24,25 Floor DB packing | 1
|  | Man power | 3
| 1 | 2nd floor corridor conduting | 4
| 2 | 3103 wiring | 2
| 3 | 27th toilet Work | 2
|  | Man power | 8
| 1 | 2nd &4th floor corridor conduting | 4
| 2 | 31st wiring | 4
|  | Man power | 8
| 1 | 5th 6th floor corridor conduting | 4
| 2 | 3203 wiring | 2
| 3 | 30 ledgewall | 2
| 4 | 27th toilet Work | 2
|  | Man power | 10
| 1 | 7th floor corridor wiring | 2
| 2 | 31&31 flat wiring | 2
| 3 | 28th floor toilte work | 2
| 4 | 31 floor ledge wall | 1
| 5 | 8th floor foot lamp fixing | 1
|  | Man power | 8
| 1 | 7th floor corridor wiring | 2
| 2 | 2301 checking | 2
| 3 | 14th floor toilte work | 2
| 4 | lmr room and earth strip | 4
| 5 | 4th floor lp marking | 2
|  | Man power | 12
| 1 | 7th floor corridor wiring | 2
| 2 | 2301 wiring checking | 2
| 3 | earth strip work | 2
| 4 | 31 st toilet Work | 2
|  | Man power | 8
| 1 | 24th floor checking | 2
| 2 | 24 th flooe foot lamp cutting | 2
| 3 | earth strip work | 1
|  | Man power | 5
| 1 | 24Th floor checking | 2
| 2 | 24th floor foootlamp cutting chepping | 2
| 3 | Lmr room | 2
|  | Man power | 6
| 1 | 24th floor foootlamp cutting chepping | 2
| 2 | 2nd floor c | 2
| 3 | Toilte work | 1
| 4 | Phase 2 basment temporary lighting | 2
|  | Man power | 7
| 1 | corridor work | 2
| 2 | 2nd floor actuators fixing | 2
| 3 | phase 2 basment temporary lighting | 2
|  | Man power | 6
| 1 | lift rectification | 2
| 2 | 2nd floor actuators fixing | 1
| 3 | FAPA Counduting | 1
|  | Man power | 4
| 1 | Club house slab conduiting | 4
| 2 | 2nd floor actuators fixing | 2
| 3 | 17th floor FAPA Counduting | 2
|  | Man power | 8
| 1 | 5th floor LP marking | 2
| 2 | 17th floor FAPA Counduting | 1
|  | Man power | 3
| 1 | 27th floor tagging | 2
| 2 | 3rd floor Ac socket fixing | 3
| 3 | 25th floor FAPA Counduting | 2
|  | Man power | 7
| 1 | 29th floor tagging | 2
| 2 | 4th floor GLD wiring | 2
| 3 | 28th floor FAPA Counduting | 2
|  | Man power | 6
| 1 | 24th floor checking | 2
| 2 | 4th floor GLD wiring | 2
| 3 | 28th floor fa points | 2
| 4 | 2nd floor corridor wiring | 2
| 5 | 4th floor LP marking | 2
|  | Man power | 10
| 1 | 31st floor tagging | 2
| 2 | 5th floor GLD Wiring | 2
| 3 | 2nd floor corridor wiring | 2
| 4 | 503 LP marking | 2
|  | Man power | 8
| 1 | 2402&2403 checking | 2
| 2 | 2nd floor corridor wiring | 2
| 3 | 503 LP marking | 2
|  | Man power | 6
| 1 | 25th floor checking | 2
| 2 | 5th floor GLD Wiring | 2
| 3 | 503 LP marking | 2
|  | Man power | 6
| 1 | 3101&3102 tagging | 2
|  | Man power | 2
| 1 | 22nd floor snag points | 2
| 2 | 8th floor GLD Wiring | 2
| 3 | 6th floor LP marking | 2
|  | Man power | 6
| 1 | 22nd floor snag points | 2
| 2 | 4th floor snag points | 2
| 3 | 6th floor LP marking | 2
|  | Man power | 6
| 1 | 25th floor snag points | 2
| 2 | 4th loor snag points | 2
| 3 | 6th floor LP marking | 3
| 4 | 32nd floor wiring | 2
| 5 | 25th &26 floor footlamp cutting chepping | 2
| 6 | 2nd MEADB | 2
|  | Man power | 13
| z | 25th floor snag points | 2
| 2 | 4th loor snag points | 2
| 3 | 6th floor LP marking | 2
| 4 | 27th floor checking | 2
| 5 | 25th &26 floor footlamp cutting chepping | 2
| 6 | 2nd MEADB | 2
|  | Man power | 12
| 1 | 7th floor LP marking | 2
| 2 | 27th floor checking | 2
| 3 | 25th &26 floor footlamp cutting chepping | 2
| 4 | 2nd MEADB | 1
|  | Man power | 5
| 1 | 7th floor marking LP | 3
| 2 | ODU connection | 1
| 3 | earth strip power | 1
|  | Man power | 5
| 1 | 8th floor marking LP | 3
| 2 | MAEDB instalation | 6
|  | Man power | 9
| 1 | 2nd floor MAEDB Dressing | 4
| 2 | 9th floor Lp marking | 2
| 3 | 25th floor snag points | 2
|  | Man power | 8
| 1 | 2nd floor MAEDB Dressing | 4
| 2 | 9th floor Lp marking | 3
| 3 | 26th floor snag points | 2
|  | Man power | 9
| 1 | 2nd floor MAEDB Dressing | 4
| 2 | 9th floor Lp marking | 3
| 3 | 26th floor snag points | 2
|  | Man power | 9
| 1 | 2nd floor MAEDB Dressing | 2
| 2 | 2nd floor corridor | 2
| 3 | 32 floor wiring | 2
|  | Man power | 6
| 1 | 25th floor snag points | 2
| 2 | 7th and 8th floor LP snag points | 2
| 3 | 3rd floor Ac socket fixing | 1
|  | Man power | 5
| 1 | 32nd floor wiring | 2
| 2 | 2nd floor corridor | 1
|  | Man power | 3
| 1 | 32nd floor wiring | 2
|  | Man power | 2
| 1 | 32nd floor flexible and dummy fixing | 2
|  | Man power | 2
| 1 | 32nd floor wiring | 2
| 2 | 2nd floor corridor | 1
|  | Man power | 2
| 1 | 27th floor checking | 2
| 2 | 2nd floor corridor | 1
|  | Man power | 3
| 1 | 27th floor checking | 2
| 2 | 2nd floor corridor | 3
|  | Man power | 5
| 1 | 27th floor checking | 2
| 2 | 9th and 8th floor LP marking | 2
| 3 | lift -2 | 2
|  | Man power | 6
| 1 | 27th floor checking | 2
| 2 | 12th floor checking | 2
| 3 | lift -2 | 2
|  | Man power | 6
| 1 | 27th floor checking | 2
| 2 | 15th floor marking | 2
| 3 | lift -2 | 2
|  | Man power | 6
| 1 | 2nd floor corridor Lp marking | 1
| 2 | lift -2 | 2
|  | Man power | 3
| 1 | 2nd floor corridor Lp marking | 1
| 2 | lift -2 | 3
|  | Man power | 4
| 1 | 27th floor checking | 2
| 2 | 2nd floor corridor | 2
| 3 | lift -2 | 3
|  | Man power | 7
| 1 | staircase checking | 1
| 2 | lift -2 | 3
|  | Man power | 4
| 1 | Earth strip laying | 1
| 2 | 2nd floor corridor | 2
| 3 | 6th floor Ac socket fixing | 3
|  | Man power | 5
| 1 | Earth strip laying | 1
| 2 | 6th floor Ac socket fixing | 2
|  | Man power | 3
| 1 | Earth strip laying | 1
| 2 | 8th floor Ac socket fixing | 2
|  | Man power | 3
| 1 | GLD wiring | 1
| 2 | 13th floor footlamp fixing | 1
|  | Man power | 2
| 1 | 2nd floor | 1
| 2 | RO conduit | 1
|  | Man power | 2
| 1 | 27th floor cutting chepping | 2
| 2 | 301 switch board | 2
|  | Man power | 4
| 1 | 27th floor cutting chepping | 2
|  | Man power | 2
| 1 | 28th floor cutting chepping | 4
| 2 | 301 switch board | 2
|  | Man power | 6
| 1 | 301 switch board | 2
|  | Man power | 2
| 1 | 32th floor cutting chepping | 2
| 2 | 303 ferrol & box cleaning | 4
|  | Man power | 6
| 1 | 303 ferrol & box cleaning | 2
| 2 | 3rd floor corridor | 2
| 3 | 303 ferrol & box cleaning | 2
| 4 | 29th floor checking | 2
|  | Man power | 8
| 1 | 30th floor cutting chepping | 2
| 2 | 3rd floor corridor | 2
| 3 | 303 ferrol & box cleaning | 2
|  | Man power | 6
| 1 | 301 switch board fixing | 2
|  | Man power | 2
| 1 | 303 Switch Board fixing | 2
| 2 | 3rd floor corridor wiring | 2
| 3 | 4th floor corridor wiring | 2
| 4 | 5th floor corridor wiring | 2
| 5 | Earth strip laying | 2
|  | Man Power | 10
| 1 | 303 Switch Board fixing | 2
| 2 | 3rd floor corridor wiring | 2
| 3 | 4th floor corridor wiring | 1
| 4 | 27th floor snag points | 2
| 5 | Earth strip laying | 1
|  | Man Power | 8
| 1 | 303 Switch Board fixing | 2
| 2 | 3rd floor corridor wiring | 2
| 3 | 4th floor corridor wiring | 1
| 4 | 27th floor snag points | 2
|  | Man Power | 7
| 1 | 302 AEDB dressing | 2 | AEDB Ferrules WIP
| 2 | 7th floor corridor wiring | 2 | Not engaged | Manpower Shited to 403 Theft Circuit Laying
| 3 | External LPS Conductor Laying | 1 | Completd
|  | Man Power | 5
| 1 | 302 AEDB dressing | 1 | AEDB Ferrules WIP |  | 1503 Slab Monitoring Worker | 1
| 2 | 7th floor corridor wiring | 2 | Not engaged | Manpower Shited to 403 Theft Circuit Laying | 1601 Box fixing &Wall | 3
| 3 | 28th floor snag points | 2 | Completd |  | 1602 Wall | 3
|  | Man Power | 5 |  |  | Man Power | 5
| 1 | 302 AEDB dressing | 1 | Not engaged | Man power shifted to 303 Box fixing | 1601 Wall & Slab | 5
| 2 | 4th floor corridor wiring | 2 | Completd |  | 1602 Wall | 2
| 3 | 26th floor snag points | 2 | WIP 50%
|  | Man Power | 5 |  |  | Man Power | 7
| 1 | 302 switch Board | 2 | WIP (60% -completed) |  | 1601 Wall & Slab | 1
| 2 | 7th floor corridor wiring | 2 | WIP (80%-completed) |  | 1602 Wall | 6
| 3 | 26th floor snag points | 2 | completd
|  | Man Power | 6 |  |  | Man Power | 7
20-11-2025 | 1 | 1st floor wiring | 2 | WIP (60% -completed) |  | 1603 wall conduit | 2
| 2 | 8th floor corridor wiring | 4 | WIP (10%-completed) |  | 1701 BOX fixing | 3
| 3 | 6th floor corridor wiring | 2 | WIP (10% - completed) |  | Material Packing | 2
|  | Man Power | 8 |  |  | Man Power | 7
21-11-2025 | 1 | 1st floor wiring | 2 | WIP (70% -completed) |  | 1603 wall conduit slab | 5
| 2 | 8th floor corridor wiring | 2 | WIP (10%-completed) |  | 1602 screw open & 1701 Bax fixing | 2
| 3 | 401 ferrol fixing | 2 | WIP (30% -completed)
| 4 | 5th floor corridor wiring | 2 | completed
|  | Man Power | 8 |  |  | Man Power | 7
22-11-2025 | 1 | 1st floor wiring | 2 | WIP (80% -completed) |  | 1603 wall conduit slab & 1701 Wall | 5
| 2 | 6th floor corridor wiring | 2 | WIP (20%-completed) |  | 1702 Bax fixing | 2
| 3 | 401 ferrol fixing | 2 | WIP (30% -completed) |  | 701 thread pulling | 3
|  | Man Power | 6 |  |  | Man Power | 10
24-11-2025 | 1 | foot lamp marking | 1 | WIP (13th floor working ) |  | 1701 Wall & slab | 6
| 2 | 29 th floor Wiring snag points | 2 | wip |  | 1702 Wall conduit | 2
| 3 | 401 ferrol fixing | 2 | WIP (50% -completed) |  | 1703 Box fixing | 2
| 4 | 5th floor corridor wiring | 2 | completed (Unit 3 pending)
|  | Man Power | 7 |  |  | Man Power | 10
25-11-2025 | 1 | 1st floor wiring | 2 | WIP (80% completed ) |  | 1701 Slab corridor | 2
| 2 | 29 th floor Wiring snag points | 2 | wip (28th floor working ) |  | 1702wall conduit | 2
| 3 | 401 ferrol fixing | 1 | WIP (50% -completed) |  | 6th floor corridor thread pulling | 2
| 4 | 6th floor corridor wiring | 2 | WIP (60% - completed) |  | 1703 Box fixing & wall | 3
|  | Man Power | 7 |  |  | Man Power | 9
26-11-2025 | 1 | 1st floor wiring | 2 | WIP (80% completed ) |  | 1703 wall conduit | 2
| 2 | 3rd floor 302 Switch board fixing | 2 | WIP (50% -completed) |  | 1702 wall & slab | 6
| 3 | Earth strip laying | 1 | completed |  | 6th floor corridor thread pulling | 2
|  | Man Power | 5 |  |  | Man Power | 10

## Match-2026DLR -NOV -25
DLR& DPR Details
Contractor : Dayakar Electricals
| Date | Tower -B |  |  |  | Tower -E
|  |  | Planned Works | Manpower (No's) | Work Status By EOD/ DPR |  | Planned Works | Manpower (No's) | Work Status By EOD/ DPR
|  | 1 | 2203 checking | 2
|  | 2 | 2nd floor mockup | 2
|  | 3 | 12&13 floor DB | 2
|  | 4 | staircase | 2
|  |  | Total | 8
|  | 1 | 29 floor communication | 2
|  | 2 | 21th floor toilet | 2
|  | 3 | staire case wiring | 1
|  | 4 | 12th floor toilet wiring | 2
|  |  | Total | 7
|  | 1 | 23 floor toilet wiring | 2
|  | 2 | 30th floor communication | 2
|  | 3 | 202 Switch board fixing | 3
|  | 4 | 1st floor foot lamp work | 2
|  |  | Total | 9
|  | 1 | 30th floor communication | 2
|  | 2 | 202 Switch board fixing | 3
|  | 3 | 1st floor foot lamp work | 2
|  |  | Total | 7
|  | 1 | 2203 Checking | 2
|  | 2 | 13th floor flat | 4
|  | 3 | 2nd floor foot lamp work | 2
Total
|  | 1 | 16th floor toilet | 2
|  | 2 | 2nd floor foot lamp work | 2
Total
|  | 1 | 12th & 13th floor DB | 1
|  | 2 | 2nd floor | 1
Total
|  | 1 | 22 floor communication | 1
|  | 2 | 14th floor DB | 1
|  | 3 | lift shaft work | 3
|  | 4 | 19th floor foot lamp | 2
Total
|  | 1 | 2203 Continuity Checking | 2
|  | 2 | lift shaft work | 4
|  | 3 | 19th floor foot lamp | 2
Total
|  | 1 | 3002 flexible fixing | 1
|  | 2 | lift shaft work | 2
|  | 3 | 20th floor foot lamp | 2
Total
|  | 1 | 3002 flexible fixing | 1
|  | 2 | lift shaft work | 3
Total
|  | 1 | lift shaft work | 3
|  | 2 | 17th floor toilet | 2
|  | 3 | 3001 Ac Box fixing | 2
|  | 4 | 17th Fa Points | 2
|  |  | Total | 9
|  | 1 | lift shaft work | 3
|  | 2 | B1 Slab Conduiting | 2
|  | 3 | 12th&13th Floor DB | 1
|  |  | Total | 6
|  | 1 | lift shaft work | 3
|  | 2 | Club House | 2
|  |  | Total | 5
|  | 1 | lift shaft work | 3
|  | 2 | B1 Slab Conduiting | 2
|  | 3 | 3rd Floor Corridor | 2
|  |  | Total | 7
|  | 1 | 12th floor DB packing | 2
|  | 2 | B1 Slab Conduiting | 2
|  | 3 | 3rd Floor Corridor | 2
|  |  | Total | 6
|  | 1 | 13 Floor DB packing | 2
|  |  | Total | 2
|  | 1 | 11 th floor toilet | 2
|  | 2 | 16th floor toilet | 2
|  | 3 | 31st floor DB Fixing | 2
|  | 4 | 3rd floor celling lp marking | 2
|  |  | Total | 8
|  | 1 | 3rd floor corridor | 2
|  | 2 | B1 Slab Conduiting | 2
|  | 3 | 31st floor DB Fixing | 2
|  | 4 | 2303 checking | 2
|  |  | Total | 8
|  | 1 | 3rd floor corridor | 2
|  | 2 | 3rd floor Board cleaning | 2
|  | 3 | 2nd floor QC points | 2
|  | 4 | 16th DB packing | 2
|  |  | Total | 8
|  | 1 | 3rd floor corridor | 2
|  | 2 | 3rd floor Board cleaning | 2
|  | 3 | 31st floor Knx Wiring | 2
|  | 4 | 16th and 15th toilet Work | 2
|  |  | Total | 8
|  | 1 | 3rd floor corridor | 3
|  | 2 | 5th floor corridor wiring | 3
|  | 3 | 31st floor communication | 2
|  | 4 | 15th toilet Work | 1
|  |  | Total | 9
|  | 1 | 3rd floor corridor | 4
|  | 2 | 5th floor corridor wiring | 3
|  | 3 | 17th18 toilet Work | 2
|  |  | Total | 9
|  | 1 | 17thtoilet Work | 2
|  |  | Total | 2
|  | 1 | 4rd floor corridor | 2
|  | 2 | 6th floor corridor wiring | 2
|  |  | Total | 4
|  | 1 | 4rd floor corridor | 2
|  | 2 | 7th floor corridor wiring | 2
|  | 3 | 2303 Checking | 2
|  |  | Total | 6
|  | 1 | 6rd floor corridor | 2
|  | 2 | 7th floor corridor wiring | 2
|  | 3 | 2302 Checking | 2
|  |  | Total | 6
|  | 1 | 8rd floor corridor | 2
|  | 2 | 7th floor corridor wiring | 2
|  | 3 | 2302 Checking | 2
|  |  | Total | 6
|  | 1 | 3102 wiring | 2
|  |  | Total | 2
|  | 1 | 3201 wiring | 2
|  |  | Total | 2
|  | 1 | 18th floor DB Packing | 1
|  | 2 | 22nd floor DB | 1
|  | 3 | 4th floor LP marking | 2
|  | 4 | 18th toilet Work | 2
|  |  | Total | 6
|  | 1 | 22nd floor snag | 2
|  | 2 | 4th floor LP marking | 2
|  | 3 | 24th floor toilte work | 2
|  | 4 | 201 QC snag points | 1
|  | 5 | 22nd floor cutting chepping | 2
|  |  | Total | 9
|  | 1 | 26th Floor toilte work | 2
|  | 2 | 2nd floor corridor conduting | 2
|  | 3 | passanger lift2 open conduting | 2
|  | 4 | 22nd floor cutting chepping | 2
|  |  | Total | 8
|  | 1 | 18th Floor toilte work | 2
|  | 2 | 2nd floor corridor conduting | 2
|  | 3 | passanger lift2 open conduting | 2
|  | 4 | 2302&201 checking | 2
|  |  | Total | 8
|  | 1 | 2nd floor corridor conduting | 2
|  | 2 | 3103 wiring | 2
|  | 3 | 401 LP marking | 2
|  | 4 | 27th toilet Work | 2
|  |  | Total | 8
|  | 1 | 2nd floor corridor conduting | 2
|  | 2 | 23,24,25 Floor DB packing | 1
|  |  | Total | 3
|  | 1 | 2nd floor corridor conduting | 4
|  | 2 | 3103 wiring | 2
|  | 3 | 27th toilet Work | 2
|  |  | Total | 8
|  | 1 | 2nd &4th floor corridor conduting | 4
|  | 2 | 31st wiring | 4
|  |  | Total | 8
|  | 1 | 5th 6th floor corridor conduting | 4
|  | 2 | 3203 wiring | 2
|  | 3 | 30 ledgewall | 2
|  | 4 | 27th toilet Work | 2
|  |  | Total | 10
|  | 1 | 7th floor corridor wiring | 2
|  | 2 | 31&31 flat wiring | 2
|  | 3 | 28th floor toilte work | 2
|  | 4 | 31 floor ledge wall | 1
|  | 5 | 8th floor foot lamp fixing | 1
|  |  | Total | 8
|  | 1 | 7th floor corridor wiring | 2
|  | 2 | 2301 checking | 2
|  | 3 | 14th floor toilte work | 2
|  | 4 | lmr room and earth strip | 4
|  | 5 | 4th floor lp marking | 2
|  |  | Total | 12
|  | 1 | 7th floor corridor wiring | 2
|  | 2 | 2301 wiring checking | 2
|  | 3 | earth strip work | 2
|  | 4 | 31 st toilet Work | 2
|  |  | Total | 8
|  | 1 | 24th floor checking | 2
|  | 2 | 24 th flooe foot lamp cutting | 2
|  | 3 | earth strip work | 1
|  |  | Total | 5
|  | 1 | 24Th floor checking | 2
|  | 2 | 24th floor foootlamp cutting chepping | 2
|  | 3 | Lmr room | 2
|  |  | Total | 6
|  | 1 | 24th floor foootlamp cutting chepping | 2
|  | 2 | 2nd floor c | 2
|  | 3 | Toilte work | 1
|  | 4 | Phase 2 basment temporary lighting | 2
|  |  | Total | 7
|  | 1 | corridor work | 2
|  | 2 | 2nd floor actuators fixing | 2
|  | 3 | phase 2 basment temporary lighting | 2
|  |  | Total | 6
|  | 1 | lift rectification | 2
|  | 2 | 2nd floor actuators fixing | 1
|  | 3 | FAPA Counduting | 1
|  |  | Total | 4
|  | 1 | Club house slab conduiting | 4
|  | 2 | 2nd floor actuators fixing | 2
|  | 3 | 17th floor FAPA Counduting | 2
|  |  | Total | 8
|  | 1 | 5th floor LP marking | 2
|  | 2 | 17th floor FAPA Counduting | 1
|  |  | Total | 3
|  | 1 | 27th floor tagging | 2
|  | 2 | 3rd floor Ac socket fixing | 3
|  | 3 | 25th floor FAPA Counduting | 2
|  |  | Total | 7
|  | 1 | 29th floor tagging | 2
|  | 2 | 4th floor GLD wiring | 2
|  | 3 | 28th floor FAPA Counduting | 2
|  |  | Total | 6
|  | 1 | 24th floor checking | 2
|  | 2 | 4th floor GLD wiring | 2
|  | 3 | 28th floor fa points | 2
|  | 4 | 2nd floor corridor wiring | 2
|  | 5 | 4th floor LP marking | 2
|  |  | Total | 10
|  | 1 | 31st floor tagging | 2
|  | 2 | 5th floor GLD Wiring | 2
|  | 3 | 2nd floor corridor wiring | 2
|  | 4 | 503 LP marking | 2
|  |  | Total | 8
|  | 1 | 2402&2403 checking | 2
|  | 2 | 2nd floor corridor wiring | 2
|  | 3 | 503 LP marking | 2
|  |  | Total | 6
|  | 1 | 25th floor checking | 2
|  | 2 | 5th floor GLD Wiring | 2
|  | 3 | 503 LP marking | 2
|  |  | Total | 6
|  | 1 | 3101&3102 tagging | 2
|  |  | Total | 2
|  | 1 | 22nd floor snag points | 2
|  | 2 | 8th floor GLD Wiring | 2
|  | 3 | 6th floor LP marking | 2
|  |  | Total | 6
|  | 1 | 22nd floor snag points | 2
|  | 2 | 4th floor snag points | 2
|  | 3 | 6th floor LP marking | 2
|  |  | Total | 6
|  | 1 | 25th floor snag points | 2
|  | 2 | 4th loor snag points | 2
|  | 3 | 6th floor LP marking | 3
|  | 4 | 32nd floor wiring | 2
|  | 5 | 25th &26 floor footlamp cutting chepping | 2
|  | 6 | 2nd MEADB | 2
|  |  | Total | 13
|  | z | 25th floor snag points | 2
|  | 2 | 4th loor snag points | 2
|  | 3 | 6th floor LP marking | 2
|  | 4 | 27th floor checking | 2
|  | 5 | 25th &26 floor footlamp cutting chepping | 2
|  | 6 | 2nd MEADB | 2
|  |  | Total | 12
|  | 1 | 7th floor LP marking | 2
|  | 2 | 27th floor checking | 2
|  | 3 | 25th &26 floor footlamp cutting chepping | 2
|  | 4 | 2nd MEADB | 1
|  |  | Total | 5
|  | 1 | 7th floor marking LP | 3
|  | 2 | ODU connection | 1
|  | 3 | earth strip power | 1
|  |  | Total | 5
|  | 1 | 8th floor marking LP | 3
|  | 2 | MAEDB instalation | 6
|  |  | Total | 9
|  | 1 | 2nd floor MAEDB Dressing | 4
|  | 2 | 9th floor Lp marking | 2
|  | 3 | 25th floor snag points | 2
|  |  | Total | 8
|  | 1 | 2nd floor MAEDB Dressing | 4
|  | 2 | 9th floor Lp marking | 3
|  | 3 | 26th floor snag points | 2
|  |  | Total | 9
|  | 1 | 2nd floor MAEDB Dressing | 4
|  | 2 | 9th floor Lp marking | 3
|  | 3 | 26th floor snag points | 2
|  |  | Total | 9
|  | 1 | 2nd floor MAEDB Dressing | 2
|  | 2 | 2nd floor corridor | 2
|  | 3 | 32 floor wiring | 2
|  |  | Total | 6
|  | 1 | 25th floor snag points | 2
|  | 2 | 7th and 8th floor LP snag points | 2
|  | 3 | 3rd floor Ac socket fixing | 1
|  |  | Total | 5
|  | 1 | 32nd floor wiring | 2
|  | 2 | 2nd floor corridor | 1
|  |  | Total | 3
|  | 1 | 32nd floor wiring | 2
|  |  | Total | 2
|  | 1 | 32nd floor flexible and dummy fixing | 2
|  |  | Total | 2
|  | 1 | 32nd floor wiring | 2
|  | 2 | 2nd floor corridor | 1
|  |  | Total | 2
|  | 1 | 27th floor checking | 2
|  | 2 | 2nd floor corridor | 1
|  |  | Total | 3
|  | 1 | 27th floor checking | 2
|  | 2 | 2nd floor corridor | 3
|  |  | Total | 5
|  | 1 | 27th floor checking | 2
|  | 2 | 9th and 8th floor LP marking | 2
|  | 3 | lift -2 | 2
|  |  | Total | 6
|  | 1 | 27th floor checking | 2
|  | 2 | 12th floor checking | 2
|  | 3 | lift -2 | 2
|  |  | Total | 6
|  | 1 | 27th floor checking | 2
|  | 2 | 15th floor marking | 2
|  | 3 | lift -2 | 2
|  |  | Total | 6
|  | 1 | 2nd floor corridor Lp marking | 1
|  | 2 | lift -2 | 2
|  |  | Total | 3
|  | 1 | 2nd floor corridor Lp marking | 1
|  | 2 | lift -2 | 3
|  |  | Total | 4
|  | 1 | 27th floor checking | 2
|  | 2 | 2nd floor corridor | 2
|  | 3 | lift -2 | 3
|  |  | Total | 7
|  | 1 | staircase checking | 1
|  | 2 | lift -2 | 3
|  |  | Total | 4
|  | 1 | Earth strip laying | 1
|  | 2 | 2nd floor corridor | 2
|  | 3 | 6th floor Ac socket fixing | 3
|  |  | Total | 5
|  | 1 | Earth strip laying | 1
|  | 2 | 6th floor Ac socket fixing | 2
|  |  | Total | 3
|  | 1 | Earth strip laying | 1
|  | 2 | 8th floor Ac socket fixing | 2
|  |  | Total | 3
|  | 1 | GLD wiring | 1
|  | 2 | 13th floor footlamp fixing | 1
|  |  | Total | 2
|  | 1 | 2nd floor | 1
|  | 2 | RO conduit | 1
|  |  | Total | 2
|  | 1 | 27th floor cutting chepping | 2
|  | 2 | 301 switch board | 2
|  |  | Total | 4
|  | 1 | 27th floor cutting chepping | 2
|  |  | Total | 2
|  | 1 | 28th floor cutting chepping | 4
|  | 2 | 301 switch board | 2
|  |  | Total | 6
|  | 1 | 301 switch board | 2
|  |  | Total | 2
|  | 1 | 32th floor cutting chepping | 2
|  | 2 | 303 ferrol & box cleaning | 4
|  |  | Total | 6
|  | 1 | 303 ferrol & box cleaning | 2
|  | 2 | 3rd floor corridor | 2
|  | 3 | 303 ferrol & box cleaning | 2
|  | 4 | 29th floor checking | 2
|  |  | Total | 8
|  | 1 | 30th floor cutting chepping | 2
|  | 2 | 3rd floor corridor | 2
|  | 3 | 303 ferrol & box cleaning | 2
|  |  | Total | 6
|  | 1 | 301 switch board fixing | 2
|  |  | Total | 2
|  | 1 | 303 Switch Board fixing | 2
|  | 2 | 3rd floor corridor wiring | 2
|  | 3 | 4th floor corridor wiring | 2
|  | 4 | 5th floor corridor wiring | 2
|  | 5 | Earth strip laying | 2
|  |  | Total | 10
|  | 1 | 303 Switch Board fixing | 2
|  | 2 | 3rd floor corridor wiring | 2
|  | 3 | 4th floor corridor wiring | 1
|  | 4 | 27th floor snag points | 2
|  | 5 | Earth strip laying | 1
|  |  | Total | 8
|  | 1 | 303 Switch Board fixing | 2
|  | 2 | 3rd floor corridor wiring | 2
|  | 3 | 4th floor corridor wiring | 1
|  | 4 | 27th floor snag points | 2
|  |  | Total | 7
|  | 1 | 302 AEDB dressing | 2 | AEDB Ferrules WIP
|  | 2 | 7th floor corridor wiring | 2 | Not engaged
|  | 3 | External LPS Conductor Laying | 1 | Completd
|  |  | Total | 5
|  | 1 | 302 AEDB dressing | 1 | AEDB Ferrules WIP |  | 1503 Slab Monitoring Worker | 1
|  | 2 | 7th floor corridor wiring | 2 | Not engaged |  | 1601 Box fixing &Wall | 3
|  | 3 | 28th floor snag points | 2 | Completd |  | 1602 Wall | 3
|  |  | Total | 5 |  |  | Total | 5
|  | 1 | 302 AEDB dressing | 1 | Not engaged |  | 1601 Wall & Slab | 5
|  | 2 | 4th floor corridor wiring | 2 | Completd |  | 1602 Wall | 2
|  | 3 | 26th floor snag points | 2 | WIP 50%
|  |  | Total | 5 |  |  | Total | 7
|  | 1 | 302 switch Board | 2 | WIP (60% -completed) |  | 1601 Wall & Slab | 1
|  | 2 | 7th floor corridor wiring | 2 | WIP (80%-completed) |  | 1602 Wall | 6
|  | 3 | 26th floor snag points | 2 | completd
|  |  | Total | 6 |  |  | Total | 7
| 2025-11-20 | 1 | 1st floor wiring | 2 | WIP (60% -completed) |  | 1603 wall conduit | 2
|  | 2 | 8th floor corridor wiring | 4 | WIP (10%-completed) |  | 1701 BOX fixing | 3
|  | 3 | 6th floor corridor wiring | 2 | WIP (10% - completed) |  | Material Packing | 2
|  |  | Total | 8 |  |  | Total | 7
| 2025-11-21 | 1 | 1st floor wiring | 2 | WIP (70% -completed) |  | 1603 wall conduit slab | 5
|  | 2 | 8th floor corridor wiring | 2 | WIP (10%-completed) |  | 1602 screw open & 1701 Bax fixing | 2
|  | 3 | 401 ferrol fixing | 2 | WIP (30% -completed)
|  | 4 | 5th floor corridor wiring | 2 | completed
|  |  | Total | 8 |  |  | Total | 7
| 2025-11-22 | 1 | 1st floor wiring | 2 | WIP (80% -completed) |  | 1603 wall conduit slab & 1701 Wall | 5
|  | 2 | 6th floor corridor wiring | 2 | WIP (20%-completed) |  | 1702 Bax fixing | 2
|  | 3 | 401 ferrol fixing | 2 | WIP (30% -completed) |  | 701 thread pulling | 3
|  |  | Total | 6 |  |  | Total | 10
| 2025-11-24 | 1 | foot lamp marking | 1 | WIP (13th floor working ) |  | 1701 Wall & slab | 6
|  | 2 | 29 th floor Wiring snag points | 2 | wip |  | 1702 Wall conduit | 2
|  | 3 | 401 ferrol fixing | 2 | WIP (50% -completed) |  | 1703 Box fixing | 2
|  | 4 | 5th floor corridor wiring | 2 | completed (Unit 3 pending)
|  |  | Total | 7 |  |  | Total | 10
| 2025-11-25 | 1 | 1st floor wiring | 2 | WIP (80% completed ) |  | 1701 Slab corridor | 2
|  | 2 | 29 th floor Wiring snag points | 2 | wip (28th floor working ) |  | 1702wall conduit | 2
|  | 3 | 401 ferrol fixing | 1 | WIP (50% -completed) |  | 6th floor corridor thread pulling | 2
|  | 4 | 6th floor corridor wiring | 2 |  |  | 1703 Box fixing & wall | 3
|  |  | Total | 7 |  |  | Total | 9
| 2025-11-26 | 1 | 1st floor wiring | 2 | WIP (80% completed ) |  | 1703 wall conduit | 2
|  | 2 | 3rd floor 302 Switch board fixing | 2 | WIP (50% -completed) |  | 1702 wall & slab | 6
|  | 3 | Earth strip laying | 1 | completed |  | 6th floor corridor thread pulling | 2
|  |  | Total | 5 |  |  | Total | 10
| 2025-11-27 | 1 | 1st floor wiring | 2 | WIP (unit -3 pending ) |  | 1702 Slab corridor | 4
|  | 2 | B2 cutting chepping | 1 | Completed |  | 1703 wall conduit | 3
|  | 3 | 401 ferrol fixing | 2 | completed
|  | 4 | 6th floor corridor wiring | 2 | WIP (point wiring completed)
|  |  | Total | 7 |  |  | Total | 7
| 2025-11-28 | 1 | 3rd floor MAEDB fixing | 2 | WIP
|  | 2 | 1st floor wiring | 2 | WIP (unit -3 pending ) |  | 1702 Screw open | 3
|  | 3 | 29 th floor Wiring snag points | 2 | WIP (flat internal completed main incoming wiring pending ) |  | 1703 wall conduit | 3
|  | 4 | 401 switch board fixing | 1 | Completed |  | 1801 Box fixing | 2
|  | 5 | 6th floor corridor wiring | 2 | Not engaged (6th floor thrifted circuits WIP) |  | 701 thread pulling | 2
|  |  | Total | 9 |  |  | Total | 10
| 2025-11-29 | 1 | 3rd floor MAEDB Fixing | 2 | WIP |  | 1703 slab conduit | 6
|  | 2 | 401 ferrol fixing | 1 | WIP |  | 1801 wall | 2
|  | 3 | 6th floor corridor wiring | 2 | WIP (point wiring completed) |  | 6th floor corridor | 2
|  |  | Total | 5 |  |  | Total | 10
| 2025-11-30 | [5 empty] | 1703 slab conduit | 3
[7 empty] | 1801 wall | 3
|  |  | SUNDAY |  |  |  | 1802 BOX fixing | 4
[7 empty] | Total | 10
| 2025-12-01 | 1 | 1st floor wiring | 2 | WIP (unit -3 pending )
|  | 2 | B2 cutting chepping | 2 | completed |  | 1802 wall | 2
|  | 3 | 401 switch board fixing | 3 | Completed |  | 1801 Box fixing | 4
|  | 4 | 6th floor corridor wiring | 2 | Not engaged (6th floor thrifted circuits WIP)
|  |  | Total | 9 |  |  | Total | 6
| 2025-12-02 | 1 | 1st floor wiring | 2 | WIP (unit -3 WIP )
|  | 2 | B2 cutting chepping | 1 | completed |  | 1802 wall conduiting | 5
|  | 3 | 401 switch board fixing | 3 | Completed |  | 1801 slab conduiting | 2
| 2025-12-03 |  | Total | 6 |  |  | Total | 7
|  | 1 | 1st floor wiring | 2 | WIP (unit -3 WIP )
|  | 2 | 6th floor thrifted wiring | 2 | completed (7th floor WIP) |  | 1802 wall conduiting | 5
|  | 3 | 401 switch board fixing | 4 | Completed (WIP 402) |  | 1801 slab conduiting | 2
|  | 4 | B2 cutting chepping | 2 | completed |  | 1802 wall conduiting | 5
|  |  | Total | 10 |  |  | Total | 6
| 2025-12-04 |  | Total | 6 |  |  | Total | 7
|  | 1 | 6th floor thrifted wiring | 2 | WIP |  | 1802 wall conduiting | 5
|  | 2 | 401 switch board fixing | 2 | Completed (WIP 402) |  | 1801 slab conduiting | 2
|  | 3 | 7th and 8th floor LP snag points | 4 | 7th floor unit 3 WIP |  | 1802 wall conduiting | 5
|  |  | Total | 8 |  |  | Total | 6
| 2025-12-05 | 1 | 401 switch board fixing | 3 | Completed (WIP 402) |  | 1802 slab conduiting & 1901 Box fixing | 5
|  | 2 | 7th and 8th floor LP snag points | 4 | completed |  | 1803 wall conduiting 7 temporary lighting staircase | 4
|  |  | Total | 7 |  |  | Total | 9
|  | 1 | 9th floor laying theft circuit | 2 | WIP (unit -3 WIP )
| 2025-12-08 | 2 | switch Board fixing 601 | 3 | WIP(AEDB dressing ) |  | 1802 wall conduiting | 5
|  | 3 | 17th floor foot lamp Back box | 2 | completed |  | 1801 slab conduiting | 2
|  | 4 | toilet marking 7th to 11th floor | 2 | No man power up to 2 Pm |  | 1802 wall conduiting | 5
|  |  | Total | 9 |  |  | Total | 6
|  | 1 | 9th floor laying theft circuit | 2 | 1003 wip (1001 pending)
| 2025-12-09 | 2 | switch Board fixing 601 | 3 | WIP(AEDB dressing ) |  | 1803 slab monitoring | 1
|  | 3 | 17th floor foot lamp Back box | 2 | No man power |  | 1901 slab conduiting | 6
|  | 4 | 9th floor corridor | 2 | WIP |  | 1902 wall conduiting | 2
|  |  | Total | 9 |  |  | Total | 9
| 2025-12-10 | 1 | 10th floor laying theft circuit | 2 | 1003 wip ( MAN POWER Engaged in Basment work ) |  | 1803 screw open | 2
|  | 2 | switch Board fixing 601 | 3 | WIP(AEDB dressing ) |  | 1902 wall conduiting | 3
|  | 3 | 17th floor foot lamp Back box | 1 | No man power |  | 1901 slab conduiting | 2
|  |  | Total | 6 |  |  | Total | 7
| 2025-12-11 | 1 | 6th floor corridor wiring | 2 | WlP point wiring completed
|  | 2 | 4th floor switch fixing | 2 | WIP
|  | 3 | 3rd floor MAEDB fixing | 2 | Completed (DB fixing)
|  |  | Total | 6 |  |  | Total | 7
| 2025-12-12 | 1 | 7th floor corridor wiring | 2 | Completed
|  | 2 | 6th floor switch Board fixing | 2 | 601 WIP
|  | 3 | 3rd floor | 2 | MADB fixing
|  | 4 | 8th 9th 10th floor Balcony & toilte marking | 1 | WIP (10th floor 1&3 units pending)
|  |  | Total | 7 |  |  | Total | 7
| 2025-12-13 | 1 | 6th floor corridor wiring | 2 | WIP
|  | 2 | 6th floor switch Board fixing | 4 | 601 WIP
|  | 3 | 9th floor corridor wiring | 2 | WIP point wiring completed
|  | 4 | 10th floor Balcony & toilte marking | 1 | Completed
|  |  | Total | 9 |  |  | Total | 7
| 2025-12-15 | 1 | 6th floor corridor wiring | 2 | Checking completed ( Snag WIP)
|  | 2 | 6th floor switch Board fixing | 2 | 601 WIP
|  | 3 | 4th floor MADB fixing | 2 | WIP
|  | 4 | 1st floor wiring | 2 | WIP
|  |  | Total | 8 |  |  | Total | 7
| 2025-12-16 | 1 | 8th floor corridor wiring | 2 | point wiring completed (WIP)
|  | 2 | 6th floor switch Board fixing | 2 | 601 WIP
|  | 3 | 4th floor MADB fixing | 2 | WIP (401 )
|  | 4 | 1st floor wiring | 2 | WIP
|  |  | Total | 8 |  |  | Total | 7
v | 2025-12-17 | 1 | 8th floor corridor wiring | 2 | point wiring completed (WIP)
|  | 2 | 6th floor switch Board fixing | 3 | 601 WIP
|  | 3 | 4th floor MADB fixing | 2 | WIP (401 )
|  | 4 | 9th floor corridor | 2 | WIP
|  |  | Total | 9 |  |  | Total | 7
F1-12-12-2025 | 2025-12-18 | 1 | 8th floor corridor wiring | 2 | Point wiring completed (WIP)
|  | 2 | 6th floor switch Board fixing & MABD | 4 | 602 WIP (601 Completed)
|  | 3 | 9th &10 floor corridor | 4 | WIP
|  |  | Total | 10 |  |  | Total | 7
| 2025-12-19 | 1 | 6th floor switch Board fixing & MABD | 2 | 602 WIP (601 Completed)
|  | 2 | 9th &10 floor corridor | 4 | WIP (8th floor completed QC checking pending)
|  |  | Total | 6 |  |  | Total | 7
F1-12-12-2025 | 2025-12-20 | 1 | 603 theft circuits | 2 | WIP ( 3 points pending)
|  | 2 | 6th floor switch Board fixing & MABD | 3 | 602 WIP (601 checking Completed)
|  | 3 | 9th &10 floor corridor | 6 | WIP
|  |  | Total | 11 |  |  | Total | 7
F1-12-12-2025 | 2025-12-22 | 1 | 1st floor RO Conduit Work | 2 | Completed |  | 2002 Slab & 2003 Wall | 6
|  | 2 | 6th floor switch Board fixing & MABD | 4 | 602 WIP
|  | 3 | 11th &10 floor corridor | 6 | WIP
|  |  | Total | 12 |  |  | Total | 7
| 2025-12-23 | 1 | 6th floor switch Board fixing & MABD | 4 | 602 WIP
|  | 2 | 11th &10 floor corridor | 6 | 11 WIP (10th completed QC checking pending)
|  |  | Total | 10 |  |  | Total | 7
| 2025-12-24 | 1 | 6th floor switch Board fixing & MABD | 3 | 602 WIP
|  | 2 | 11th &10 floor corridor | 5 | 11 WIP (10th completed QC checking also Completed)
|  |  | Total | 8 |  |  | Total | 7
v | 2025-12-26 | 1 | 11th & 12th floor corridor wiring | 6 | 11th completed ( 12thWIP)
|  | 2 | 6th floor switch Board fixing | 2 | 603 WIP
|  | 3 | 26th floor | 2 | WIP
|  | 4 | 16th floor corridor | 3 | WIP
|  |  | Total | 13 |  |  | Total | 7
v | 2025-12-27 | 1 | 13th & 14th floor corridor wiring | 6 | 11th & 12th QC checking completed ( 13th & 14th WIP )
|  | 2 | 603 WIP | 4 | 603 WIP
|  | 3 | 3rd floor DB dressing | 2 | WIP
|  |  | Total | 12 |  |  | Total | 7
v | 2025-12-28 | 1 | 13th & 14th floor corridor wiring | 6 | WIP ( 13th & 14th WIP ) |  | 2102 SLAB | 4
|  | 2 | 28th floor cutting chepping | 5 | Completed |  | 2103 Wall | 2
|  | 3 | 7th floor Switch Boards | 2 | WIP |  | 10th floor thread pulling | 4
|  |  | Total | 13 |  |  | Total | 10
v | 2025-12-29 | 1 | 13th & 14th floor corridor wiring | 5 | WIP |  | 2103 Wall & slab | 5
|  | 2 | 7th floor switch Board fixing | 4 | WIP |  | 2201 Box fixing | 2
|  | 3 | 28th floor foot lamp fixing | 2 | WIP |  | 10th floor thread pulling | 3
|  | 4 | 29th and 28th snag points | 2 | WIP
|  |  | Total | 14 |  |  | Total | 10
v | 2025-12-31 | 1 | 13th & 14th floor corridor wiring | 6 | WIP |  | 2103 Wall & slab | 5
|  | 2 | 7th floor switch Board fixing | 4 | WIP |  | 2201 Box fixing | 2
|  | 3 | 29th and 28th snag points | 2 | WIP
|  |  | Total | 12 |  |  | Total | 10
v | 2026-01-02 | 1 | 15th & 14th floor corridor wiring | 6 | WIP |  | 2103 Wall & slab | 5
|  | 2 | 7th floor switch Board fixing | 4 | WIP |  | 2201 Box fixing | 2
|  |  | Total | 10 |  |  | Total | 10
v | 2025-01-03 | 1 | 18th & 19th floor corridor wiring | 6 | WIP |  | 2201Wall & slab | 3
|  | 2 | 7th floor switch Board fixing | 4 | WIP |  | 2203 Box fixing | 2
|  | 3 | 26th floor foot lamp fixing | 1 | Completed |  | 11th floor thread pulling | 2
|  | 4 | 26th snag points | 2 | Completed |  | 2202 Wall & 12th Box open | 4
|  |  | Total | 13 |  |  | Total | 11
v | 2025-01-05 | 1 | 18th & 19th floor corridor wiring | 6 | WIP |  | 2201Wall & slab | 3
|  | 2 | 7th floor switch Board fixing | 5 | WIP |  | 2203 Box fixing | 2
|  | 3 | 11th snag points | 2 | Completed |  | 2202 Wall & 12th Box open | 4
|  |  | Total | 13 |  |  | Total | 11
v | 2025-01-06 | 1 | 18th & 19th floor corridor wiring | 6 | WIP
|  | 2 | 7th floor switch Board fixing | 4 | WIP |  | 2203 Box fixing | 3
|  | 3 | 6th floor DB dressing | 1 | WIP (10% - completed) |  | 11th floor thread pulling | 3
|  | 4 | 11th snag points | 2 | WIP |  | Corridor | 2
|  |  | Total | 13 |  |  | Total | 8
v | 2025-01-07 | 1 | 18th & 19th floor corridor wiring | 6 | WIP (14th to 16th floor QC checking completed)
|  | 2 | 7th floor switch Board fixing | 4 | WIP |  | 2203Wall & slab | 2
|  | 3 | 6th floor DB dressing | 1 | WIP (20% - completed) |  | 11th floor thread pulling | 3
|  | 4 | 11th snag points | 2 | Completed |  | 2202 Corridor & SLAB | 4
|  |  | Total | 13 |  |  | Total | 9
v | 2025-01-08 | 1 | 20th & 19th floor corridor wiring | 6 | WIP (17th to 18th floor QC checking completed) |  | 2301 Box fixing | 2
|  | 2 | 7th floor switch Board fixing | 4 | WIP |  | 2203Wall & slab | 2
|  | 3 | 6th floor DB dressing | 1 | WIP (30% - completed) |  | 11th floor thread pulling | 3
|  | 4 | 12th & 13th floor snag points | 2 | Not engaged manpower |  | 2202 Corridor & SLAB | 2
|  |  | Total | 13 |  |  | Total | 9
v | 2025-01-09 | 1 | 20th & 19th floor corridor wiring | 6 | WIP |  | 2301 Wall counduting | 2
|  | 2 | 7th floor switch Board fixing | 3 | WIP |  | 2203Wall & slab | 2
|  | 3 | 6th floor DB dressing | 1 | WIP (40% - completed) |  | 11th floor thread pulling | 3
|  | 4 | 11th &12th toilet light marking | 2 | WIP |  | Material packing | 2
|  |  | Total | 12 |  |  | Total | 9
v | 2025-01-10 | 1 | 20th & 19th floor corridor wiring | 6 | WIP |  | 2301 Wall counduting | 2
|  | 2 | 7th floor switch Board fixing | 3 | WIP |  | 2203 Corridor & slab | 2
|  | 3 | 6th floor DB dressing | 1 | WIP (50% - completed) |  | 11th floor thread pulling | 3
|  | 4 | 11th &12th toilet light marking &29th floor cutting chipping | 4 | WIP |  | Material packing | 1
|  |  | Total | 14 |  |  | Total | 8
v | 2025-01-11 | 1 | 20th & 19th floor corridor wiring | 6 | WIP |  | 2301 Wall counduting | 2
|  | 2 | 7th floor switch Board fixing | 3 | WIP |  | Material packing | 3
|  | 3 | 4th floor DB dressing | 1 | WIP (30% - completed) |  | 12th floor thread pulling | 3
|  | 4 | stair case & 27th foot lamps | 4 | WIP
|  |  | Total | 14 |  |  | Total | 8
v | 2025-01-12 | 1 | 20th & 19th floor corridor wiring | 6 | WIP |  | 2301 Wall counduting | 3
|  | 2 | 8th floor switch Board fixing | 3 | WIP (7th floor completed QC checking pending) |  | 2302 wall | 2
|  | 3 | 4th floor DB dressing | 1 | WIP (30% - completed) |  | 12th floor thread pulling | 3
|  | 4 | stair case & 29th foot lamps | 4 | WIP |  | 16th floor Box open | 1
|  |  | Total | 14 |  |  | Total | 9
v | 2025-01-13 | 1 | 21st floor corridor wiring | 6 | WIP |  | 2301 Slab counduting | 2
|  | 2 | 8th floor switch Board fixing | 3 | WIP |  | 2302 wall & 2303 wall | 4
|  | 3 | 4th floor DB dressing | 1 | WIP (30% - completed) |  | 12th floor thread pulling | 2
|  |  | Total | 14 |  |  | Total | 8
v | 2025-01-14 | 1 | 20th & 19th floor corridor wiring | 6 | WIP |  | 2301 Slab counduting | 2
|  | 2 | 8th floor switch Board fixing | 3 | WIP (7th floor completed QC checking pending) |  | 2302 wall | 2
|  | 3 | 4th floor DB dressing | 1 | WIP (30% - completed) |  | 12th floor thread pulling | 2
|  | 4 | stair case & 29th foot lamps | 4 | WIP |  | 2303th floor Box fixing | 2
|  |  | Total | 14 |  |  | Total | 8

## Match-2026Sheet1
DLR& DPR Details
Contractor : Dayakar Electricals
Date | Tower -B |  |  | Tower -E
|  | Planned Works | Manpower (No's) |  | Planned Works | Manpower (No's) | Work Status By EOD/ DPR
| 1 | 5th floor (501 Maedb ) | 2 |  | 2803 SLAB | 2 | completd
2026-03-01 | 2 | 56th floor lihght fixing | 2 |  | 2901 Box fixing &wall | 2
| 3 | 12th floor ceiling rose(1203) | 2 |  | Material packing | 3
| 4 | corridor piping and corridor wire (1st floor ) | 2 |  | 27th floor corridor | 2
| 5 | 16th floor AEDB adjustment | 2 |  | 28th floor JB open | 1
|  | 16th floor laying theft circuit | 2 |  | 22 & 23 rd pending works | 2
| Tootal- | Total Manpower | 12 |  | Totel Manpower | 12
2026-03-02 | 1 | 5th floor AEDB dressing (501) | 2 |  | 2803 screw open | 2
| 2 | 5th floor MAED (501) | 2 |  | 2901` Wall | 2
| 3 | 27th floor laying incoming | 4 |  | 2902 Box fixing | 3
| 4 | 16th floor laying theft circuit | 2 |  | 28th floor JB open | 1
[5 empty] | 22 & 23rd floor pending work | 2
| Tootal- | Total Manpower | 10 |  | Totel Manpower | 10
2026-03-03 | 1 | 501 AEDB Dressing | 2 |  | 2901 SLAB | 6
| 2 | 27thvfloor 10sqmm laying | 2 |  | 2902 Wall | 2
| 3 | 1st floor corridor wiring | 2 |  | 2903 Box fixing | 2
| 4 | 18 and 19th floor AC sockets fixing | 2 |  | 22 & 23rd floor pending works | 2
| 5 | 501 MAEDB Dressing | 2
| Tootal- | Total Manpower | 10 |  | Totel Manpower | 12
2026-03-04 |  | NO man power |  |  | No man power
|  | 9th floor Switch Board fixing |  |  | 2902 Wall
[5 empty] | 2903 Box fixing | 2
[5 empty] | Material packing | 2
[5 empty] | 28th THREAD Pulling | 2